## Identified Risks
Bradford Transforming Care Programme Risk Register | [7 empty] | Risk Level
Private and Confidential | [6 empty] | High | 12 to 16
V No. | 0.1 | [5 empty] | Medium | 6 to 9
Last updated: Insert Date |  |  | 2016.02.22 |  |  |  | Low | 1 to 4
Unique risk number within each project area | (Financial, (O)perational, (R)eputational | C – Corporate D – Department S – Service M – Cross Department | DESCRIPTION of Risk to the successful achievement of the Programme Objectives, presented under category headings (Business, Project or Stage) | Likelihood of occurrence: 1= Low 4=Very High | Impact on Programme Objectives: 1=Low 4=Very High | Level of Risk (Likelihood multiplied by impact) | Statutory or Discretionary | Short term (immediate), Medium term (up to 6 months) or Long term (more than 6 months) | Action's proposed in order to manage the risk or the current measures that are in place to control the risk. (Accept, reject, transfer or risk reduction) | Name of person who initially identified and logged the risk | Person responsible for leading action | Identified, Open, Closed, Rejected | Comments
BDF TCP 1 | F,O,R | M | Financial risks - managing this system change within the budget cuts across the health and social care economy. | 4 | 4 | 16 | S | S, M, L | Senior managements teams across health and social care reporting on risk nmanagement toH&WB | Mairead O' Donnell | tbc | Open
BDF TCP 2 | F,O,R | M | Double funding of people moving from low secure to community settings | 3 | 3 | 9 | S | S,M,L |  | Mairead O' Donnell | tbc | Open
BDF TCP 3 | F,O,R | M | Manging the dowry which is fixed around how long people have been in hospital | 4 | 3 | 12 | S | S,M,L | The system holds this risk - needs managing with support from NHS England | Mairead O' Donnell | tbc | Open
BDF TCP 4 | F,O,R | M | Resources required to deliver this agenda within the required timescales across all services. | 4 | 4 | 16 | S | S, M, L | As the programme develops it will become clearer as to the resource impact on delvering this programme | Mairead O' Donnell | tbc | Open
BDF TCP 5 | F,O,R | M | Developing a Dynamic Risk Register | 3 | 3 | 9 | S | S,M,L |  | Mairead O' Donnell | tbc | Open
BDF TCP 6 | F,O,R | M | Our ability to develop the market place of specialist and skilled providers in order to develop the alternative support model to in patient services. It will take time to develop a responsive marketplace to respond to the situation of finding alternative appropriate service provision should high cost providers refuse to negotiate costs | 4 | 4 | 16 | S | S,M,L | This is potentially a high risk area if we do not have providers responding to the procurement process for this specialist area. Following the 'Intention To Tender' stage of the procurement process - it will be clearer what the market response will be and what action we need to take. | Mairead O' Donnell | tbc | Open
BDF TCP7 | F,O,R | M | Difficulty in recruitment a skilled workforce – care sector is competing with better paid industries in the area. | 3 | 3 | 9 | S | S.M.L |  | Mairead O' Donnell | tbc | Open
BDF TCP 8 | F,O,R | M | The impact of this changed approach on ‘mainstream’ in patient and community services. | 2 | 3 | 6 | S | S.M.L |  | Mairead O' Donnell | tbc | Open
BDF TCP 9 | F,O,R | M | The capital money available to develop the new respite service and housing on the Branshaw site, plus Weaver Court is still awaiting allocation. | 4 | 4 | 16 | S | S.M.L |  | Mairead O' Donnell | tbc | Open
BDF TCP 10 | F,O,R | M | Engagement of mainstream services on this agenda. | 2 | 3 | 6 | S | S.M.L |  | Mairead O' Donnell | tbc | Open
BDF TCP 11 | F,O,R | M | Different IT systems will limit the ability to share data | 3 | 4 | 12 | S | S.M.L |  | Mairead O' Donnell | tbc | Open

## Risk Summaries
|  | Summary of Total Risk Scores | Number of Risks
|  | Low Risk | 0
|  | Medium Risk | 5
|  | High Risk | 6
4
3
2
1
| 1 | 2 | 3 | 4
Impact

## Closed Risks
Closed Risks | [7 empty] | Risk Level
[7 empty] | High | 12 to 16
[7 empty] | Medium | 6 to 9
[7 empty] | Low | 1 to 4
Unique risk number within each project area | (Financial, (O)perational, (R)eputational | C – Corporate D – Department S – Service M – Cross Department | DESCRIPTION of Risk to the successful achievement of the Programme Objectives, presented under category headings (Business, Project or Stage) | Likelihood of occurrence: 1= Low 4=Very High | Impact on Programme Objectives: 1=Low 4=Very High | Level of Risk (Likelihood multiplied by impact) | Statutory or Discretionary | Short term (immediate), Medium term (up to 6 months) or Long term (more than 6 months) | Action's proposed in order to manage the risk or the current measures that are in place to control the risk. (Accept, reject, transfer or risk reduction) | Name of person who initially identified and logged the risk | Person responsible for leading action | Identified, Open, Closed, Rejected
1.17 | F,O, R | D,S | Commissioning and housing need to have clear information from operational commissioning in order to plan for services in a timely way. Without this people will be placed in inappropriate and/or costly services which may be out of area. | 2 | 2 | 4 | S | S,M,L | A housing planning group have been set up and are meeting monthly. However JH has now left the dept and no one taking the leadership of this group yet. | Mairead O' Donnell |  | Closed | Next meeting planned for 1st September 2015
1.19 | F,O,R | D,S | There is pressure on the commissioning and contracts team to manage the procurement activity linked to the Home Care and Residential Framework and the day to day work around decommissioning (such as SJOG). | 3 | 2 | 6 | S | S,M,L | Take to the programme board to discuss further | Mairead O' Donnell | Chris Cobb | Closed | The view from the senior amangement team was that this activity had to managed within existing resources.

## Document Control
| Risk Register | LD, MH, PD programme
Document Information
| Created by: | Mairead O' Donnell
| Date of Creation: | 19th February 2016
Document is only valid for date of creation. Latest version can be requested from the PMO
Purpose: To capture all risks for the (insert project name) and provide a means by which to document and track each risk
Revision History
Version No: | Date | Editor | Description of Changes
0.1

## Issues Log (hidden)
Issue ref | Workstream | Issue Description | Actions required | Status | Owner | Review date or frequency | Links/ comments
| Education | Where and how will payments to schools be made from August 2011
| Education | Support needed to support heads understand financial risks with budgeting