## Lists
Design Schedule and Scheme Costs
| Project: | Queensbury Tunnel Greenway Feasibility Study
| Compiled by: | KA/MT/AG/ML
| Document ref: | 10533-N-SC-02-0000-01
| Date Updated: | 2022-10-05
|  |  |  | Construction Costs |  | Non-construction up-front costs
Corridor List |  | Sheet Number | Tab Name | Construction Only Rate (per unit) | Unit | Item | % | How applied
Halifax to Holmfield | [5 empty] | Ecology | 15 | Calculated as percentage of construction costs without preliminaries. Applied to individual links.
Halifax to Holmfield: Greenway Option |  |  | Design Schedule |  |  | Land & Legal | 10 | Calculated as percentage of construction costs without preliminaries. Applied to individual links.
|  |  | Scheme Costs |  |  | Construction Preliminaries | 15 | Calculated as percentage of construction costs without preliminaries. Applied to whole scheme.
Halifax to Holmfield: Highway Option |  | 1 | Uncontrolled crossing | 10950 | No | Contingency | 10 | Calculated as percentage of construction costs with preliminaries. Applied to whole scheme.
Alpine Option |  | 2 | Controlled Crossing | 96500 | No | Design & Development | 8 | Calculated as percentage of construction costs with preliminaries and contingency. Applied to whole scheme.
Tunnel Option |  | 3 | Controlled Crossing (Separated) | 160000 | No
West Bradford: Clayton Option |  | 4 | Zebra Crossing | 28656 | No
West Bradford: Thornton Option |  | 5 | Zebra Crossing (Separated) | 41500 | No
Keighley to Cullingworth |  | 6 | 3m Wide Shared Path | 155 | m | Operation and Maintenance | % | How applied
Cullingworth to Queensbury |  | 7 | 4.5m Wide Shared Path | 188 | m | Tunnels | 0.5 | Calculated as percentage of construction costs without preliminaries. Applied to individual links.
|  | 8 | 5m Wide Shared Path | 230 | m | Non-tunnel, non-highway | 5 | Calculated as percentage of construction costs without preliminaries. Applied to individual links.
|  | 9 | One-way light Separated Tracks | 120 | m | Highway | 0 | In discussion with CBMDC, highway infrastructure maintenance subsumed into separate highway budget.
|  | 10 | Bi directional Kerb Separated | 450 | m
|  | 11 | One-way Kerb Separated | 355 | m
|  | 12 | Mixed Traffic Environment | 295 | m
|  | 13 | Trotting Strip | 40 | m
|  | 14 | Resurfacing | 65 | m²
|  | 15 | Fencing | 36 | m
|  | 16 | Modal Filter | 18750 | No
|  | 17 | Street Lighting | 64 | m
|  | 18 | Street Lighting Bollards | 50 | m
|  | 19 | Bus Gate | 105000 | No
|  | 20 | Shared Path | 242 | m
|  | 21 | Improve Existing Traffic Free | 175 | m
|  | 22 | Earthworks Ramp | 1525 | m
|  | 23 | 3m Wide Shared Path on slope | 510 | m
|  | 24 | Wayfinding Signage | 225 | No
|  | 25 | Security (Tunnels) | 20000 | No
|  | 26 | Tunnel Works | 1766 | m
|  | 27 | 4m Wide Shared Tunnel Path | 240 | m
|  | 28 | Maintenance | Reference only, applied as percentage

## Design Schedule
|  | Segment Ref | [9 empty] | Design Challenges | [8 empty] | Cost Estimates: Construction | [38 empty] | Non-tunnel & bridge |  | Tunnel & bridge (structures only)
Corridor | Drawing Number | From | To | Length | Width where required | Quantity for costing | Unit | Administrative Area | Type of Provision | RoW status | Speed limit | Buildability | Stakeholder Support | Poor Coherence | Indirect | Safety Issues | Uncomfortable | Unattractive | Compliance | Summarised Challenges/Opportunities | Uncontrolled Crossing | Controlled X-ing | Controlled X-ing (Separated) | Zebra X-ing | Zebra X-ing (Separated) | 3m Wide Shared Path | 4.5m Wide Shared Path | 5m Wide Shared Path | One-way light separated tracks | Bi-Directional Kerb Separated Track | One-way kerb separated tracks | Mixed Traffic Environment | Trotting Strip | Resurfacing | Fencing | Modal Filter | Street Lighting | Lighting Bollards | Bus Gate | Shared use Path | Improve existing traffic-free route | Earthworks Ramp | 3m wide shared path on slope | Wayfinding Signage | Security (Tunnels) | Tunnel Works | 4.5m Wide Shared Tunnel Path | Bridges | Road Markings / TROs | Junction Reconfiguration | Carriageway Narrowing | Bridge Inspection and Works | Bespoke Cost | Standard Cost | Calculated Construction Cost excluding tunnel and bridge works (£) | Calculated Construction Cost tunnel and bridge works (£) | Construction Cost Estimate Notes | Ecological Assessment Required? | Land & Legal Required? | Ecology Cost | Land & Legal Cost | Ecology Cost | Land & Legal Cost | Tunnel Maintenance | Other Maintenance | Tunnel Maintenance Cost (inc. cycle & walking infrastructure) | Other (Non-tunnel) Maintenance Cost
Halifax to Holmfield |  | H101 | H102 | 136 | - | 136 | m |  | - Shared use path to eastern edge of footway | Public highway | 30 |  |  |  |  | ü | ü |  | ü | - Shared use is sub-optimal in urban space. - Route forms temporary alternative to re-alignment and extension of Hebble Trail - Use of shared path avoids need to navigate/reconfigure roundabout - May lead to some discomfort for users during busy periods - Some users may perceive as being unsafe due to interaction within other users in shared area | [19 empty] | X | [13 empty] | 242 | 32912 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H102 | H102 | - | - | 1 | No |  | - Parallel crossing over Water Lane | Public highway | 30 |  | ü | [6 empty] | - Assumption that traffic volumes are within required levels for parallel crossing provision. - Suitability will require assessment at a subsequent design stage considering traffic speeds and volumes. - Opportunity to link to Halifax Railway Station scheme delivery. |  |  |  | X | [29 empty] | 28656 | 28656 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H102 | H103 | 495 | - | - | - |  | Provision developed by others: - Traffic Free route - Junction improvements at entrance to Station from Church Street/Square Road | Public highway |  |  | ü | [6 empty] | - Provision dependent on Halifax Railway Station (TCF, WY+) | [33 empty] | 0 | - | - | Assumed funded by others |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H103 | H104 | 203 | - | 1 | No |  | - Cycling in mixed traffic environment - Create parking areas that are raised and contrast with the adjacent footways. This can then be used by pedestrians when nobody is parking and it will also serve to reduce the width of the carriageway, slowing vehicle speeds and making the environment more suitable for cycling. - Existing 20mph zone. | Public highway | 20 | [5 empty] | ü | ü | ü | - Average gradient 7%, but this route follows the existing road. - Opportunity to connect station and town centre schemes. - Gradient may serve to exclude some users who may not consider the route to be comfortable or attractive. | [30 empty] | X |  | 98252 | 0 | 98252 | - | Assumed funded by others |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H104 | H105 | 413 | - | - | - |  | Provision developed by others: - Contraflow cycle lane (southbound) - Cycling in mixed traffic (northbound) | Public highway | 20 |  | ü | [6 empty] | - Provision dependent on A629 Halifax Town Centre scheme (WY+) | [33 empty] | 0 | - | - | Assumed funded by others |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H105 | H108 | - | - | - | m |  | - One way cycle lanes in both directions. | Public highway |  |  | ü | [6 empty] | - Provision dependent on A629 Halifax Town Centre Scheme (Phase 2) (WY+) | [33 empty] | 0 | - | - | Assumed funded by others |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield | [5 empty] | - | No |  | - 4 No. junction reconfigurations. Protected space for cycles provided through all of the junctions, including right turns. | Public highway |  |  | ü | [40 empty] | 0 | - | - | Assumed funded by others |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H108 | H109 | 1537 | - | 8 | No |  | - Cycling in mixed traffic environment - Allow for 8x buildouts to narrow carriageway and calm traffic speeds between modal filters. - Speed limit reduced to 20mph | Public highway | 30 |  | ü |  |  | ü | ü | ü | ü | - Route based on section 'B' in Old Lane/Valley Floor Cycle Corridor consultation, with enhancements. - Cobbled surface of Bowling Dyke/Lower Old Lane presents comfort challenge and may require some improvement. - Gradient along Old Lane exceeds recommended maximum in LTN1/20, but is follows an existing road. - Business access from Bowling Dyke Road: route would require careful signing/narrowing to ensure safety of cycles/pedestrians. - Opportunity to implement in short term, with Valley Floor option as long-term improved provision plan. - Risk that without additional measures to enhance environment and exclude through traffic completely, route may be unattractive as approach to traffic-free stretch. - Opportunity to provide information boards where view over formal railway line is clear. - Avoids ecological challenges present along Valley Floor option. - Installation of modal filters can present a number of stakeholder / community engagement challenges. More specifically, they can be divisive schemes to implement. | [30 empty] | X |  | 5000 | 0 | 40000 | - | £5000 per buildout |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option | [5 empty] | 2 | No |  | - Installation of modal filter on Old Lane to south of Mill Lane to exclude through traffic - Installation of modal filter on Woodhouse Road to prevent access to Old Lane from east. | Public highway | [25 empty] | X | [17 empty] | 18750 | 37500 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H109 | H112 | 596 | - | 4 | No |  | - Cycling in mixed traffic environment - Allow for 4x buildouts to narrow carriageway and calm traffic speeds between modal filters. - Speed limit reduced to 20mph | Public highway | 30 |  |  |  |  | ü |  | ü |  | - Route based on section 'A' in Old Lane/Valley Floor Cycle Corridor consultation. - Installation of modal filters can present a number of stakeholder / community engagement challenges. More specifically, they can be divisive schemes to implement. - Mixed traffic environments can be perceived to be unsafe and unattractive by some users unless vehicle speeds and volumes are suitable for this approach. | [30 empty] | X |  | 5000 | 0 | 20000 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option | [5 empty] | 1 | No |  | - Installation of modal filter on Old Lane to north of Mill Lane | Public highway | 30 |  | ü | [22 empty] | X | [17 empty] | 18750 | 18750 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H109 | H110 | 127 | - | 6 | No |  | - Cycling in mixed traffic environment: reduce speed limit to 20mph on Broad Tree Road - introduce 2x buildouts every 40-50m to reduce the carriageway down to a single running lane in the centre of the road. This will formalise what looks like parking areas that have been delineated by cobbles at different orientations. Total 6x buildouts. | Public highway | 30 |  |  |  |  | ü | ü | ü | ü | - Opportunity to link greenway provision to planned TCF schemes on Ovenden Way/Ovenden Road. - Broad Tree Road is a steep, cobbled road. May not be suitable for all users. - Broad Tree Road/Mill Lane provides link between West Halifax and A647. Risk that at peak hours traffic is higher than acceptable for cycling in Mixed Traffic, leading to greater level of provision and associated programme/cost impacts. | [30 empty] | X |  | 5000 | 0 | 30000 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option | [5 empty] | 1 | No |  | - Reduced corner radius on Mill Lane / Old Lane junction to slow vehicle turning speeds | Public highway | [39 empty] | X |  |  | 5000 | 0 | 5000 | - | £5,000 per corner radii reduction. |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H110 | H204 | 188 | - | 188 | m |  | - Shared use footway on east of Ovenden Way, to link to existing crossing point location | Public highway | 30 | [7 empty] | ü | - Shared use footway does not meet criteria of LTN 1/20 by not separating users. - The risk of users finding the shared path uncomfortable, unsafe or unattractive is mitigated as the path would be linking two sections of infrastructure and footway will be used by relatively low number of pedestrians. | [19 empty] | X | [13 empty] | 242 | 45496 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H110 | H110 | - | - | 1 | No |  | - Zebra crossing over Broad Tree Road - Remove pedestrian refuge and tighten left turn exit from Broad Tree Road to Ovenden Road to provide space to join/leave shared provision. - Speed limit reduction on Broad Tree Road to 20mph. | Public highway | 30 | [7 empty] | ü | - Cycle users from Old Lane assumed to be within the carriageway at this location. - Assumption that visibility requirements for traffic turning into Old Lane from the north can be met. | [29 empty] | X |  |  | 18950 | 0 | 18950 | - | £5,000 per corner radii reduction and uncontrolled crossing at £10,950. Remove refuge and reinstate carriageway at £3,000. |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H204 | H204 | - | - | 1 | No |  | - Ovenden Way / Ovenden Road junction reconfigured to provide improved crossings for cycles between Ovenden Way and Old Lane cycle provision. | Public highway | 30 |  | ü | [6 empty] | - Current junction configuration provides safe crossing opportunities, but in multiple stages (4 required to access northern footway on Ovenden Way) - Reconfiguration may be aspirational for long-term coherence. In the meantime, the puffin crossings could be upgraded to toucan crossings. - Longer term aspiration to reconfigure the junction may generate traffic capacity concerns from the Highways Service. | [29 empty] | X |  |  | 96500 | 0 | 96500 | - | Costed as a toucan crossing for now to represent the shorter term aspirations. A full junction overhaul would generate higher costs but this isn't necessarily required to improve connectivity to the route. |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H112 | H113 | 206 | - | 206 | m |  | - Fencing on one side of path | Private land, no current RoW beyond Royd lane. | 30 | ü | ü | [6 empty] | - Assumed no need for structure across Beck from limited access available. Options exist in this location to avoid Beck by continuing along Royd Lane. - Walled section of Royd Lane is narrow - 3m maximum. Options to run alongside even if accessed between farm buildings. - Route runs through private land. Ownership is unknown. | [14 empty] | X | [18 empty] | 36 | 7416 | - |  | ü | ü | 1112.4 | 741.6 | - | - |  | ü | - | 370.8
Halifax to Holmfield: Greenway Option |  |  |  |  | - | 206 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 10300 | - |  | ü | ü | 1545 | 1030 | - | - |  | ü | - | 515
Halifax to Holmfield: Greenway Option |  |  |  |  | - | 206 | m |  | - Route access ramp | [32 empty] | X | [11 empty] | 1525 | 314150 | - |  | ü | ü | 47122.5 | 31415 | - | - |  | ü | - | 15707.5
Halifax to Holmfield: Greenway Option |  | H113 | H114 | 376 | - | 376 | m |  | -3m wide shared traffic free route. Hillside location - earthworks/retaining walls req. | Private land - no current RoW |  | ü |  |  |  | ü |  | ü |  | - Possible future development land. Opportunity to require development to provide/protect route alignment. - Slope of hillside location. - Owner details not researched. - Hillside location (side slope): 3m wide shared route would be lower cost but could aversely impact on safety, attractiveness and level of use if volumes of users is higher than expected. Wider and/or separated tracks would provide great all-year-round access for all but would be considerably more costly. - 5% gradient max; | [22 empty] | X | [10 empty] | 510 | 191760 | - |  | ü | ü | 28764 | 19176 | - | - |  | ü | - | 9588
Halifax to Holmfield: Greenway Option |  |  |  | 752 | - | 752 | m |  | - Fencing both sides of path for safety and containment of livestock | [25 empty] | X | [18 empty] | 36 | 27072 | - |  | ü | ü | 4060.8 | 2707.2 | - | - |  | ü | - | 1353.6
Halifax to Holmfield: Greenway Option |  |  |  | 376 | - | 376 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 18800 | - |  | ü | ü | 2820 | 1880 | - | - |  | ü | - | 940
Halifax to Holmfield: Greenway Option |  | H114 | H115 | 90 | 5 | 450 | m² |  | - Cycling in mixed traffic environment. Segment too short to warrant any traffic calming interventions. Traffic volumes and speeds assumed to be very low. - Resurface Kimberley Street | Un-adopted highway | 30 |  | ü | [6 empty] | - Route potentially runs through un-adopted highway. Possible challenge from residents. - Vehicle movements for parking - likely to be low in number | [13 empty] | X | [19 empty] | 65 | 29250 | - |  | ü | ü | 4387.5 | 2925 | - | - |  | ü | - | 1462.5
Halifax to Holmfield: Greenway Option |  | H115 | - | - | - | 1 | No |  | - Crossing of Churn Milk Lane - Uncontrolled Crossing with signage | Public highway | [6 empty] | ü |  |  | - Cobbled and some gradient but for a short distance only. Low traffic volume expected. | X | [32 empty] | 10950 | 10950 | - |  | ü |  | 1642.5 | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | H115 | H115a | 653 | - | 653 | m |  | - 3m wide shared traffic free route. Hillside location - earthworks/retaining walls req. | Private land - no current RoW |  | ü |  | ü |  | ü |  | ü |  | - Route runs through private land. Ownership is unknown. - Limited opportunity to provide high-quality links to settlement to west. Potential to address through development access. - Hillside location (side slope): 3m wide shared route would be lower cost but could aversely impact on safety, attractiveness and level of use if volumes of users is higher than expected. Wider and/or separated tracks would provide great all-year-round access for all but would be considerably more costly. - 5% gradient max; | [22 empty] | X | [10 empty] | 510 | 333030 | - |  | ü | ü | 49954.5 | 33303 | - | - |  | ü | - | 16651.5
Halifax to Holmfield: Greenway Option |  |  |  | 653 | - | 653 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 32650 | - |  | ü | ü | 4897.5 | 3265 | - | - |  | ü | - | 1632.5
Halifax to Holmfield: Greenway Option |  |  |  | 1306 | - | 1306 | m |  | - Fencing both sides of path for safety and containment of livestock | [25 empty] | X | [18 empty] | 36 | 47016 | - |  | ü | ü | 7052.4 | 4701.6 | - | - |  | ü | - | 2350.8
Halifax to Holmfield |  | H115a | H116 | 452 | - | 452 | m |  | - 3m wide shared traffic free route. Hillside location - earthworks/retaining walls req. | Private land - no current RoW |  | ü |  | ü |  | ü |  | ü |  | - Route runs through private land. Ownership is unknown. - Route passes close to known area of open mosaic habitat. Full ecological assessment required and ecological mitigation likely. - Limited opportunity to provide high-quality links to settlement to west. Potential to address through development access. - Hillside location (side slope): 3m wide shared route would be lower cost but could aversely impact on safety, attractiveness and level of use if volumes of users is higher than expected. Wider and/or separated tracks would provide great all-year-round access for all but would be considerably more costly. - 5% gradient max; | [22 empty] | X | [10 empty] | 510 | 230520 | - |  | ü | ü | 34578 | 23052 | - | - |  | ü | - | 11526
Halifax to Holmfield |  |  |  | 452 | - | 452 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 22600 | - |  | ü | ü | 3390 | 2260 | - | - |  | ü | - | 1130
Halifax to Holmfield |  |  |  | 904 | - | 904 | m |  | - Fencing both sides of path for safety and containment of livestock | [25 empty] | X | [18 empty] | 36 | 32544 | - |  | ü | ü | 4881.6 | 3254.4 | - | - |  | ü | - | 1627.2
Halifax to Holmfield |  | H116 | - | - | - | 1 | No |  | - Signal-controlled crossing over Brow Lane - Extension of 20mph from junction of Holdsworth Road to east of crossing point. | Public highway | 30 |  | ü | [6 empty] | -The introduction of traffic signals may generate some opposition amongst stakeholders. |  | X | [31 empty] | 96500 | 96500 | - |  | ü |  | 14475 | - | - | - |  |  | - | -
Tunnel Option |  | H116 | H214 | 385 | - | 385 | m |  | - 3m wide traffic-free shared used path | Private land - no current RoW |  | ü | [7 empty] | - Landowner agreement req., private land, ownership known. | [5 empty] | X | [27 empty] | 155 | 59675 | - |  | ü | ü | 8951.25 | 5967.5 | - | - |  | ü | - | 2983.75
Tunnel Option |  |  |  |  | - | 385 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 19250 | - |  | ü | ü | 2887.5 | 1925 | - | - |  | ü | - | 962.5
Tunnel Option |  |  |  |  | - | 385 | m |  | - Fencing (one side) |  |  | ü | [22 empty] | X | [18 empty] | 36 | 13860 | - |  | ü | ü | 2079 | 1386 | - | - |  | ü | - | 693
Tunnel Option |  | H214 | - | - | - | 1 | No |  | - User Priority Crossing of School Cote Brow (access road) | Footpath along School Cote Brow | [9 empty] | - There may be ownership issues encountered, as the access appears to only serve private premises. | X | [32 empty] | 10950 | 10950 | - |  | ü | ü | 1642.5 | 1095 | - | - |  | ü | - | 547.5
Tunnel Option |  | H214 | H215 | 195 | - | 195 | m |  | - Route access ramp - earthworks | Private land - no current RoW |  | ü | ü | [6 empty] | - Land subject to planning permission for new development (08/00654/FUL). Landowner known. - Investigate whether path proposals be included in planning application development. Contact with developer / land owner required. - Steep slope of quarry land and limited space for new ramp - may require extension of ramp within tunnel, or extended land-take on surface. - North end at tunnel portal is currently submerged and overgrown - Assume that fencing is required on one side - Ecology - through Open Mosaic & SSSI Impact Risk zone | [21 empty] | X | [11 empty] | 1525 | 297375 | - |  | ü | ü | 44606.25 | 29737.5 | - | - |  | ü | - | 14868.75
Tunnel Option |  |  |  |  | - | 195 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 9750 | - |  | ü | ü | 1462.5 | 975 | - | - |  | ü | - | 487.5
Tunnel Option |  |  |  |  | - | 195 | m |  | - Fencing. Allow for one side (195m) | [25 empty] | X | [18 empty] | 36 | 7020 | - |  | ü | ü | 1053 | 702 | - | - |  | ü | - | 351
Tunnel Option |  | H215 | H216 | 2260 | - | 2260 | m |  | - Structural works / improvements required to enable use of the tunnel as an active travel corridor. - Costed separately in Scheme Costs - Ecology and Land costs assumed borne by others in order to carry out structural works | Private land - no current RoW |  | ü | ü |  |  | ü |  |  |  | - Delivery reliant on third party renovation and ownership transfer of Queensbury Tunnel. - Route passes through tunnel - known ecological risk. Full assessment required and likely mitigation measures. Potential to add to programme and costs. - Extensive ancillary works required to ensure secure and attractive cycling environment in addition to provision of route. - Opportunity to provide landmark heritage attraction at heart of wider route. - May be personal safety issues associated with a long tunnel. Access for emergency services may be challenging, particularly when getting to the tunnel portals. | [33 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
Tunnel Option |  |  |  |  | - | 2260 | m |  | - 4.5m wide traffic free route | [37 empty] | X | [6 empty] | 240 | 542400 | - |  |  |  | - | - | - | - | ü |  | 2712 | -
Tunnel Option |  |  |  |  | - | 8 | No |  | - Security: Motion detected CCTV and secure gates at each tunnel portal | [35 empty] | X | [8 empty] | 20000 | 160000 | - |  |  |  | - | - | - | - | ü |  | 800 | -
Tunnel Option |  |  |  |  | - | 2260 | m |  | - Low level lighting through tunnel | [28 empty] | X | [15 empty] | 50 | 113000 | - |  |  |  | - | - | - | - | ü |  | 565 | -
Tunnel Option |  | H216 | H217 | 242 | - | 242 | m |  | - 4.5m wide traffic free route | Private land - no current RoW |  |  | ü | [6 empty] | - As per tunnel. - Drainage - wide boards currently placed across track, sloshing water audible below them. | [6 empty] | X | [26 empty] | 188 | 45496 | - |  | ü | ü | 6824.4 | 4549.6 | - | - |  | ü | - | 2274.8
Alpine Option |  | H116 | H117 | 1940 | - | 1940 | m |  | - 3m wide traffic free route | Private land - no current RoW. Final zig zag follows footpath then bridleway. Numerous footpaths on slope to west of zig zags, and round factory boundary to join School Cote Brow. |  | ü |  |  | ü | ü | ü | ü |  | - Route ascends through area of former mining works. Mitigation and stabilisation for construction may be required, increasing programme time and costs. - Area of former mining works now recolonised. Full ecological assessment required, and mitigation and compensation likely. - Route runs through private land. Ownership is known. - Route can be constructed to LTN1/20 gradient requirements, but will still present challenge for some users. - The route does not offer a direct route up the slope. This may be unattractive to some users, particularly those with mobility impairments. - An alpine type slope may also generate a lot of interest, which could result in higher volumes of users presenting safety issues, particularly those who may be travelling downhill at speed. | [22 empty] | X | [10 empty] | 510 | 989400 | - |  | ü | ü | 148410 | 98940 | - | - |  | ü | - | 49470
Alpine Option |  |  |  |  | - | 1940 | m |  | - Lighting required on one side of the path | [28 empty] | X | [15 empty] | 50 | 97000 | - |  | ü | ü | 14550 | 9700 | - | - |  | ü | - | 4850
Alpine Option |  |  |  |  | - | 3880 | m |  | - Fencing both sides required (livestock grazing) | [25 empty] | X | [18 empty] | 36 | 139680 | - |  | ü | ü | 20952 | 13968 | - | - |  | ü | - | 6984
Alpine Option |  | H117 | H118 | 106 | - | 106 | m |  | - Cycling in mixed traffic environment (Residential streets, parking restrictions on Roper Lane) - Roper Lane is through route. Likely to require improvements to indicate presence of cycles. - Speed limit reduced to 20mph between Ladysmith Road and Halifax Road - Improved traffic calming measures on Roper Lane between Ladysmith Road and Halifax Road. | Public highway | 30 |  | ü |  |  | ü |  |  |  | - Mixed traffic environments can be perceived to be unsafe and unattractive by some users unless vehicle speeds and volumes are suitable for this approach. Traffic volumes and 85%ile speeds on Roper Lane are unknown, but it is expected that implementation of the measures listed will provide appropriate conditions for mixed traffic cycling. | [11 empty] | X | [21 empty] | 295 | 31270 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H118 | H118 | - | - | 1 | No |  | - New controlled crossing across Halifax Road - Junction reconfiguration. Narrowed entrance and exit only at Shibden Head Lane | Public highway | 30 |  |  |  |  | ü |  |  |  | - Route crosses AADF >10,000. As such, a fully signal controlled crossing is required. | [29 empty] | X |  |  | 20950 | 0 | 20950 | - | £5,000 per corner radii reduction and uncontrolled crossing at £10,950. |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H118 | H119 | 368 | - | 2 | No |  | - Cycling in mixed traffic environment. 2x buildouts to create strategic pinch points and slow vehicles speeds. - Speed limit reduced to 20mph | Public highway | 30 |  |  |  | ü |  |  | ü |  | - This route may be perceived as being indirect and unattractive to some users, as it provides a less direct route than the High Street. The route may also be perceived as unattractive as it does require a descent, when users will have only just ascended the Alpine Ramp. However, this is considered to be a more suitable and safer route than the High Street alternative. The traffic volumes and speeds on the High Street would require separated cycling provision to be introduced, for which there is unavailable space. As such, this route represents the most logical parallel route that offers an overall acceptable level of service. | [30 empty] | X |  | 5000 | 0 | 10000 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H119 | H120 | 171 | 3 | 513 | m |  | - Traffic Free Route to be resurfaced | Private land (assumed) - no current RoW | [5 empty] | ü | ü | ü | ü | - Further investigation required to understand whether cobbles need to be retained due to heritage value. - Route passes through private land. Ownership is unknown. - Route descends to Shibden Brook to re-ascend to Long Lane. Gradients (10%) exceed guidance maximum. - The presence of irreplaceable habitat (ancient woodland) alongside this link may impact on programme times. | [13 empty] | X | [19 empty] | 65 | 33345 | - |  | ü | ü | 5001.75 | 3334.5 | - | - |  | ü | - | 1667.25
Alpine Option |  | H120 | H121 | 343 | - | 343 | m |  | - 3m wide traffic free route - Assumed no new bridge required: existing track passes over beck with wide platform | Private land - footpath | [5 empty] | ü | ü |  | ü | - Route passes through private land. Ownership is unknown. - Route passes past area of ancient woodland. Ecological assessments will be required and mitigation likely. - Working alongside a watercourse. - Gradients on ascent to Long Lane are steep (10%), which may be uncomfortable for some users. | [21 empty] | X | [11 empty] | 1525 | 523075 | - |  | ü | ü | 78461.25 | 52307.5 | - | - |  | ü | - | 26153.75
Alpine Option |  | H121 | H122 | 57 | - | 57 | m |  | - Improved existing traffic free route | Footpath | [9 empty] | - Route passes through private land. Ownership is unknown. | [20 empty] | X | [12 empty] | 175 | 9975 | - |  | ü | ü | 1496.25 | 997.5 | - | - |  | ü | - | 498.75
Alpine Option |  | H122 | H123 | - | - | 1 | No |  | - Cycling in mixed traffic environment. - Speed limit reduced to 20mph 'Modal filter east of Hazel Hurst Road | Public Highway | 30 |  | ü |  |  | ü |  |  |  | - Route has poor visibility in places. - Opportunity to close as through route and enhance environment to support mixed traffic cycling. - Installation of modal filters can present a number of stakeholder / community engagement challenges. More specifically, they can be divisive schemes to implement. - Two small local plan housing development sites are located to the east of Long Lane. Installation of a modal filter should consider the desired effect on access to these locations. | [15 empty] | X | [17 empty] | 18750 | 18750 | - |  | ü |  | 2812.5 | - | - | - |  |  | - | -
Alpine Option |  |  |  | - |  | 1 | No |  | - Proposed modal filter in the vicinity of Jonscroft to remove through traffic and reduce vehicle speeds through southern section of Long Lane where visibility is poor and carriageway width is low. | [26 empty] | X | [17 empty] | 18750 | 18750 | - |  | ü |  | 2812.5 | - | - | - |  |  | - | -
Alpine Option |  | H123 | H124 | 75 | - | 75 | m |  | - Resurfacing existing track | Footpath | [9 empty] | - Route crosses private land. Ownership unknown | [13 empty] | X | [19 empty] | 65 | 4875 | - |  | ü | ü | 731.25 | 487.5 | - | - |  | ü | - | 243.75
Alpine Option |  | H124 | H125 | 280 | - | 280 | m |  | - 3m wide traffic free route | Footpath |  |  | ü | [6 empty] | - Access required through boundary fence to recent development. | [5 empty] | X | [27 empty] | 155 | 43400 | - |  | ü | ü | 6510 | 4340 | - | - |  | ü | - | 2170
Alpine Option |  |  |  | - |  | 180 | m |  | Fence on east side of route to housing estate | [25 empty] | X | [18 empty] | 36 | 6480 | - |  | ü | ü | 972 | 648 | - | - |  | ü | - | 324
Alpine Option |  | H125 | H126 | 424 | - | 10 | No |  | - Cycling in mixed traffic environment. Create pinch points with buildouts. Provide cycle bypasses if room is sufficient. Assumed 1x buildout on each side of the road. | Public highway | 30 |  | ü | [6 empty] | - Opportunity to enhance road environment to support mixed traffic cycling. - Opportunity to use space outside Bike Mill repair shop as cycle hub. - A local plan development site (15 dwellings) is located to the south of Old Mill Dam Lane. | [30 empty] | X |  | 5000 | 0 | 50000 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H126 | H126 | - | - | 1 | No |  | - Junction reconfiguration at Old Mill Dam Lane/Brighouse Road - Protected space for cycle turning right between Brighouse Road and Old Mill Dam Lane - Reduced corner radii on all arms of the junction - Controlled crossing points provided across Brighouse Road | Public highway | 30 |  |  | ü | [5 empty] | - Existing controlled crossing to north of junction provides a safe option for pedestrians. Space for cycle turning to be managed at junction. Clear signage required on approach to junction to avoid confusion. | [29 empty] | X |  |  | 100000 | 0 | 100000 | - | Partial upgrade of junction. Does not require tactile facilitates on all arms as a result of recent mid-block crossing installation to the north of the junction. |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H126 | H127 | 150 | - | 150 | m |  | - One-way stepped cycle tracks on both sides of the road. | Public highway | 30 |  | ü | ü | [5 empty] | - The short length of cycle track within the highway environment may be perceived as being incoherent, if not considered in the wider context of the route. This is unavoidable where there are limited opportunities to maintain a similar level of provision consistently. For example, where a route moves between a traffic free environment and the highway. | [10 empty] | X | [22 empty] | 355 | 53250 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H127 | H127 | - | - | 1 | No |  | - Minor junction improvements at Brighouse Road/High Street/Sandbeds | Public highway | 30 | [8 empty] | - Junction improvements will incorporate a protected left turn for cyclists onto Brighouse Road, as well as signal infrastructure changes to provide cyclists with a head start over traffic to enable them to turn right onto Sandbeds without conflict with vehicles. | [29 empty] | X |  |  | 125000 | 0 | 125000 | - | There is less room here to make improvements to separate cyclists in space. Therefore, improvements may need to be more focussed around signal changes. The removal of dedicated turning lanes and phases would be beneficial, although the wider impacts on network operation would need to be assessed. |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H127 | H128 | 81 | - | 81 | m |  | - One-way stepped cycle tracks | Public highway | 30 |  | ü | ü | [5 empty] | - The short length of cycle track within the highway environment may be perceived as being incoherent, if not considered in the wider context of the route. This is unavoidable where there are limited opportunities to maintain a similar level of provision consistently. For example, where a route moves between a traffic free environment and the highway. | [10 empty] | X | [22 empty] | 355 | 28755 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | H128 | H128 | - | - | 1 | No |  | - Upgrade puffin crossing to toucan crossing at Station Road. | Public highway | 30 | [8 empty] | -The provision of a toucan crossing will enable cyclists to safely cross Sandbeds in order to move from a mixed traffic environment on Station Road into the westbound cycle track on Brighouse. |  | X | [31 empty] | 96500 | 96500 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H107 | H207 | 3613 | - | - | - |  | Provision developed by others: - Mixture of shared walking and cycling and two-way cycle track between Broad Street to Shroggs Road (zone 6) - Shared cycling and walking path alongside A629 Ovenden Road (Zone 5) - One way cycle track on Ovenden Way (Zone 4) - Two way cycle track on west side of Cousin Lane (Zone 6) - 3 junction improvements on Cousin Lane | Public highway | 20 |  | ü | [6 empty] | - Provision as described in TCF - funded Improved Halifax Streets for People, Zones 2, 4, 5, 6. - Delivery and quality dependent on third party. - Opportunity to connect strategic settlements into wider route provision. - Opportunity for continuous footway across side roads for whole length of Ovenden Way and Cousin Lane. - Risk that key junction existing between Ovenden Way and Cousin Lane remains unchanged. | [33 empty] | 0 | - | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H207 | H209 | 371 | - | 8 | No |  | - Cycling in mixed traffic environment. - Residential street with existing modal filter (Moor Lane) - Reduce geometry of junctions at all side roads to ensure vehicles speeds to / from Moor Lane are reduced. | Public highway | 20 | [38 empty] | X |  |  | 8000 | 0 | 64000 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H209 | H209 | - | - | 1 | No |  | - New controlled crossing over Keighley Road (>10,000 AADT) - Existing pedestrian refuge to be removed and kerb line on western side of Keighley Road built out to provide waiting area for pedestrian areas / cycles. - Corner radii reduced on Beechwood Road | Public highway | 30 | [10 empty] | X | [31 empty] | 96500 | 96500 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H209 | H210 | 530 | - | 530 | m |  | - Cycling in mixed traffic environment. - Residential streets (Beechwood Road) | Public highway | 30 | [8 empty] | - Traffic volumes on Beechwood Road unknown. Traffic survey may indicate need for additional measures to reduce traffic volume and/or speed to comply with LTN1/20. This may introduce additional cost. - Additional traffic calming measures may be required. - Opportunity to link Beechwood Park to TCF provision | [11 empty] | X | [21 empty] | 295 | 156350 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H210 | H211 | 320 | - | 320 | m |  | Improved existing traffic free route | Public park | [9 empty] | - Local nature reserve. Additional ecological survey may be required and need for mitigation measures possible. | [20 empty] | X | [12 empty] | 175 | 56000 | - |  | ü | ü | 8400 | 5600 | - | - |  | ü | - | 2800
Halifax to Holmfield: Highway Option |  | H211 | H212 | 263 | - | 263 | m |  | - Cycling in mixed traffic environment - Surface improvements | Public highway | 20 |  |  |  |  | ü |  |  | ü | - Pinch point on Heathy Lane acts as traffic calming measure, but this could be considered to be unsafe by some cyclists. Further assessment would be required to determine whether a priority give-way system would provide a better environment for cycling. | [11 empty] | X | [21 empty] | 295 | 77585 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H212 | H212 | - | - | 1 | No |  | - Upgrade existing zebra crossing to Toucan crossing and relocate closer to the desire line - Reduced corner radii on Holdsworth Road | Public highway | 20 | [8 empty] | - Traffic volumes on Shay Lane unknown. Speed limit 20mph at crossing point. Traffic survey may indicate that a parallel crossing is sufficient. |  | X | [31 empty] | 96500 | 96500 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | H212 | H213 | 72 | - | 1 | No |  | - Extend parking restrictions on Holdsworth Road - Reduce speed limit to 20mph | Public highway | 30 |  | ü | [6 empty] | - The introduction or extension of any parking restrictions would be subject to public consultation, during which public opposition may be encountered. | [28 empty] | X |  |  |  | 2500 | 0 | 2500 | - | Nominal rate applied for minor road marking and signage works associated with speed limit change and extension of parking restrictions. |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | H213 | H115a | 33 | - | 33 | m |  | - 3m wide shared traffic free | Bridleway | 20 | ü |  |  |  | ü |  |  | ü | - Link to Holdsworth Road - Ownership of land is unknown. - Gradient of east end may be steep (buildability/compliance). - Part of link is bounded by high security fencing . Potential for users to feel unsafe. Can be mitigated with lighting in this area. | [22 empty] | X | [10 empty] | 510 | 16830 | - |  |  | ü | - | 1683 | - | - |  | ü | - | 841.5
Halifax to Holmfield |  |  |  | 46 | - | 46 | m |  | - Fencing (total length shown) | [25 empty] | X | [18 empty] | 36 | 1656 | - |  |  | ü | - | 165.6 | - | - |  | ü | - | 82.8
Halifax to Holmfield |  |  |  | 87 | 3 | 261 | m² |  | - Resurfacing, 8m wide | [24 empty] | X | [19 empty] | 65 | 16965 | - |  |  | ü | - | 1696.5 | - | - |  | ü | - | 848.25
West Bradford: Clayton Option |  | B202 | B101 | 534 | - | 534 | m |  | - Cycling in mixed traffic environment | Public highway. Back Great Russell Street part-adopted. | 30 |  |  |  |  | ü |  |  |  | '- Traffic volumes on Preston Street unknown. Traffic survey may indicate need for additional measures to reduce traffic volume and/or speed to comply with LTN1/20. This may introduce additional cost. - Opportunity to link into Thornton Road TCF cycle superhighway. Potential to make this link further west if more appropriate. | [11 empty] | X | [21 empty] | 295 | 157530 | - |  |  | ü | - | 15753 | - | - |  |  | - | -
West Bradford: Clayton Option |  |  |  | - | - | 1 | No |  | Modal filter to create appropriate traffic volumes on Preston Street. | Public Highway | [25 empty] | X | [17 empty] | 18750 | 18750 | - |  |  | ü | - | 1875 | - | - |  |  | - | -
West Bradford: Clayton Option |  | B101 | B101a | 136 | - | 136 | m |  | - 4.5m wide traffic free route round the edge of recreation ground | Private land - no current RoW |  |  | ü | [6 empty] | - Aligned round edge of recreation ground - Ownership not known | [6 empty] | X | [26 empty] | 188 | 25568 | - |  | ü | ü | 3835.2 | 2556.8 | - | - |  | ü | - | 1278.4
West Bradford: Clayton Option |  | B101a | B102 | 343 | - | 343 | m |  | - 4.5m wide traffic free route through wooded and sloping area, may be challenging; suitability not confirmed | Private land - no current RoW |  | ü | [7 empty] | - Site not accessible, not visited -Appears from desk study to be dense wooded area and on steep slope - Ownership not known - Likely to present ecological, access and buildability challenges that would require further investigation at a subsequent design stage. | [6 empty] | X | [26 empty] | 188 | 64484 | - |  | ü | ü | 9672.6 | 6448.4 | - | - |  | ü | - | 3224.2
West Bradford: Clayton Option |  | B102 | B103 | 250 | - | 250 | m |  | - Bi-Directional separated cycle track to avoid conflict point at the wide and open entrance to Wickes. | Private land - no current RoW |  | ü | ü | [6 empty] | - Access road to Wickes and others. East end is in private fenced-off land - ownership and suitability not known. Road width approx. 7m; footpath +2.4m - Adjacent to water course, possible construction implications - Wickes may have some objections to the access road being modified, particularly if it is used for the movement of HGVs. | [9 empty] | X | [23 empty] | 450 | 112500 | - |  | ü | ü | 16875 | 11250 | - | - |  | ü | - | 5625
West Bradford: Clayton Option |  | B103 | - | - | - | 1 | No |  | - Proposed Toucan Crossing, Ingleby Road | Public highway | 30 | [10 empty] | X | [31 empty] | 96500 | 96500 | - |  | ü |  | 14475 | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B103 | B104 | 312 | - | 312 | m |  | - 4.5m wide traffic free route through green scrubland area, fairly open with some areas of woodland. | Private land - no current RoW |  | ü |  |  |  | ü |  |  |  | - Route runs through private land. Ownership is unknown. - Works would be required next to a water course, with implications construction approach. - Known ecological areas of interest, requiring ecological assessment and possible mitigation. - Local development sites (employment, housing) are located to the south of the proposed route. Opportunity to deliver/safeguard route alignment as part of development. | [6 empty] | X | [26 empty] | 188 | 58656 | - |  | ü | ü | 8798.4 | 5865.6 | - | - |  | ü | - | 2932.8
West Bradford: Clayton Option |  | B104 | B105 | 222 | - | 222 | m |  | - Existing shared path developed by others, alongside ASDA - No improvements identified | Private land (assumed) - no current RoW | [9 empty] | - The proposed facility appears to be a 3m wide shared path, with an assumed sealed surface. | [33 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B105 | B108 | 60 | - | 120 | m |  | - Proposed new shared use footways on either side of Cemetery Road. Utilise existing toucan crossings over Cemetery Road | Public highway | 30 | [8 empty] | - Shared use provision in urban areas are not generally recommended. However they are acceptable in order to provide continuity for a route. | [19 empty] | X | [13 empty] | 242 | 29040 | - |  | ü |  | 4356 | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B108 | B109 | 229 | 4 | 916 | m² |  | Resurface existing private access road. | Private land - current footpath |  |  | ü | [6 empty] | - Upgrade from footpath to Bridleway required - Use of private driveway may result in objections from the landowner, who is not currently known. - Gradient is 1:13 for approx. 50m - exceeds recommended maximum for short section. | [13 empty] | X | [19 empty] | 65 | 59540 | - |  | ü | ü | 8931 | 5954 | - | - |  | ü | - | 2977
West Bradford: Clayton Option | [5 empty] | 229 | m |  | -Lighting required on one side of access road. | [28 empty] | X | [15 empty] | 50 | 11450 | - |  | ü | ü | 1717.5 | 1145 | - | - |  | ü | - | 572.5
West Bradford: Clayton Option |  | B109 | B110 | 235 | - | 235 | m |  | - Construct 3m wide traffic free route through an existing narrow PRoW trodden through overgrowth, earthworks may be required to flatten/stabilise side slope. | Private land - current footpath |  | ü | ü | [5 empty] | ü | - Route passes through private land. Ownership unknown. - Route requires bridleway application | [22 empty] | X | [10 empty] | 510 | 119850 | - |  | ü | ü | 17977.5 | 11985 | - | - |  | ü | - | 5992.5
West Bradford: Clayton Option | [5 empty] | 235 | m |  | - Lighting required on one side of path. | [28 empty] | X | [15 empty] | 50 | 11750 | - |  | ü | ü | 1762.5 | 1175 | - | - |  | ü | - | 587.5
West Bradford: Clayton Option | [5 empty] | 235 | m |  | - Fencing required on the northern side. | [25 empty] | X | [18 empty] | 36 | 8460 | - |  | ü | ü | 1269 | 846 | - | - |  | ü | - | 423
West Bradford: Clayton Option |  | B110 | B111 | 222 | - | 222 | m |  | - Construct 3m wide traffic free route | Private land - current footpath |  | ü | ü | [6 empty] | - Route passes through private land (horse fields). Ownership unknown. - Constraint at Bull Greave Beck which required non-culvert solution to pass over beck - Route requires bridleway application - Potentially realigning around field edge (not shown) would be less intrusive but if north field edge used, would mean use of steeper section of Deep Lane at north end, which also would require upgrade from footpath to bridleway. | [5 empty] | X | [27 empty] | 155 | 34410 | - |  | ü | ü | 5161.5 | 3441 | - | - |  | ü | - | 1720.5
West Bradford: Clayton Option |  |  |  |  | - | 222 | m |  | - Lighting required on one side of path. | [28 empty] | X | [15 empty] | 50 | 11100 | - |  | ü | ü | 1665 | 1110 | - | - |  | ü | - | 555
West Bradford: Clayton Option |  |  |  |  | - | 326 | m |  | - Fencing | [25 empty] | X | [18 empty] | 36 | 11736 | - |  | ü | ü | 1760.4 | 1173.6 | - | - |  | ü | - | 586.8
West Bradford: Clayton Option |  |  |  |  | - | 1 | No |  | - New bridge required to pass over Bull Greave Beck, 2-3m wide - to replace narrow footpath. Approx. 6m length currently. | [38 empty] | X |  |  |  |  | 45000 | 0 | - | 45000 | Priced as 5m wide, 6m long medium complexity bridge at £1500m² | ü | ü | - | - | 6750 | 4500 |  | ü | - | 2250
West Bradford: Clayton Option |  | B111 | B112 | 1181 | - | 1181 | m |  | - 3m wide traffic free route. - Length includes link B111a-B111b (190m) | Bridleway |  | ü |  |  |  |  | ü | ü |  | - Deep Lane is constrained by boundary fences and walls, which could create construction challenges. - Retaining wall structure likely to house bats/small mammals. Full ecological survey required, with potential implication for programme and costs. - Steep in parts (1:12 to 1:14), which could be uncomfortable and unattractive to some users. - Existing bridleway - Large local plan development site exists to the south of Deep Lane. | [5 empty] | X | [27 empty] | 155 | 183055 | - |  | ü | ü | 27458.25 | 18305.5 | - | - |  | ü | - | 9152.75
West Bradford: Clayton Option | [5 empty] | 1181 |  |  | - Lighting required on one side of path. | [28 empty] | X | [15 empty] | 50 | 59050 | - |  | ü | ü | 8857.5 | 5905 | - | - |  | ü | - | 2952.5
West Bradford: Clayton Option |  | B112 | B113a/ B114 | 642 | - | 642 | m |  | - 4.5m wide traffic free route | Bridleway (B112-113a). Footpath (B113-114). |  |  | ü | ü |  | ü |  |  |  | - Route passes through private land. Ownership unknown. - Route requires bridleway application. - Possible coherence issue between 4.5m and 3m traffic sections down Deep Lane. Consistent 3m provision may be preferable even though 4.5m possible in this section. - Route ends at busy road at B113a. | [6 empty] | X | [26 empty] | 188 | 120696 | - |  | ü | ü | 18104.4 | 12069.6 | - | - |  | ü | - | 6034.8
West Bradford: Clayton Option | [5 empty] | 642 |  |  | - Lighting required on one side of path. | [28 empty] | X | [15 empty] | 50 | 32100 | - |  | ü | ü | 4815 | 3210 | - | - |  | ü | - | 1605
West Bradford: Clayton Option |  | B113 | B114 | 183 | - | 366 | m |  | - Fencing required on both sides | Private land - current footpath | [24 empty] | X | [18 empty] | 36 | 13176 | - |  | ü | ü | 1976.4 | 1317.6 | - | - |  | ü | - | 658.8
West Bradford: Clayton Option |  | B114 | B115 | 141 | - | 141 | m |  | - 3m wide traffic free route for pedestrians/cycles only (part through private property) | Private land - current footpath |  |  | ü | [6 empty] | - Route passes through private land. A local plan development site is located on the land for a small number of dwellings. - Existing ROW would required upgrading, and proposed route preserved within any new development. | [5 empty] | X | [27 empty] | 155 | 21855 | - |  | ü | ü | 3278.25 | 2185.5 | - | - |  | ü | - | 1092.75
West Bradford: Clayton Option | [5 empty] | 141 |  |  | - Lighting required on one side of path. | [28 empty] | X | [15 empty] | 50 | 7050 | - |  | ü | ü | 1057.5 | 705 | - | - |  | ü | - | 352.5
West Bradford: Clayton Option |  | B114 | B114a | 196 | - | 196 | m |  | - Trotting strip aligned to the north side of properties to link with bridleway along Holts Lane | Private land - no current RoW | [9 empty] | - Ownership not known - Option would require further investigation | [12 empty] | X | [20 empty] | 40 | 7840 | - |  | ü | ü | 1176 | 784 | - | - |  | ü | - | 392
West Bradford: Clayton Option |  |  |  | 196 | - | 196 |  |  | Fence northern side only | [25 empty] | X | [18 empty] | 36 | 7056 | - |  |  |  | - | - | - | - |  | ü | - | 352.8
West Bradford: Clayton Option |  | B115 | B116 | 60 | - | 60 | m |  | - Cycling in mixed traffic environment (Town End Road) | Public highway | 30 |  |  |  | ü |  |  |  |  | - Opportunity to avoid navigation and reconfiguration of roundabout - Indirect link to Deep Lane may result in some users choosing substandard Bradford Road link - Traffic volumes unknown. Potential that controlled crossing required, increasing costs. | [11 empty] | X | [21 empty] | 295 | 17700 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B116 | B116 | - | - | 1 | No |  | - New parallel crossing at roundabout arm | Public highway | 30 | [13 empty] | X | [28 empty] | 41500 | 41500 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B116 | B117 | 20 | - | 20 | m |  | Shared use footway between Town End Road and The Avenue | Public highway | 30 |  |  |  |  | ü | ü | ü |  | - Depending on the volume of users, shared footways can be considered to be unsafe, unattractive and uncomfortable. This typically occurs where there are high volumes of pedestrians. | [19 empty] | X | [13 empty] | 242 | 4840 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B117 | B117 | - | - | 1 | No |  | - New parallel crossing at roundabout arm | Public highway | 30 | [13 empty] | X | [28 empty] | 41500 | 41500 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B117 | B118 | 842 | - | 1684 | m |  | - One-way stepped cycle tracks on either side of the carriageway - Parking restrictions along entire length of The Avenue | Public highway | 30 | [5 empty] | ü |  |  | - B117 to B118 forms an extended section with a gradient of approximately 5%. | [10 empty] | X | [22 empty] | 355 | 597820 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B118 | B118 | - | - | 1 | No |  | - Junction reconfiguration - Mini-roundabout replaced by a T-junction to improve safety for cycles and provide improve crossings / access between sections of cycle infrastructure | Public highway | 30 |  | ü | [6 empty] | - The introduction of a priority junction in place of a mini-roundabout may create some traffic network impacts. Discussions should be held with the highways service to understand how suitable this proposal would be from a network operation perspective. | [29 empty] | X |  |  | 80000 | 0 | 80000 | - | No signal equipment required. The junction is relatively compact and could be changed with some kerbline alterations and footway construction. |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B118 | B119 | 544 | - | 544 | m |  | - Footway build out on western side of carriageway to create 3m wide shared use space | Public highway | 30 |  |  |  |  | ü | ü | ü |  | - Depending on the volume of users, shared footways can be considered to be unsafe, unattractive and uncomfortable. This typically occurs where there are high volumes of pedestrians. | [19 empty] | X | [13 empty] | 242 | 131648 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | B119 | B120 | 138 | 5.5 | 759 | m² |  | - Existing track/highway resurfaced. | Footpath | [23 empty] | X | [19 empty] | 65 | 49335 | - |  | ü | ü | 7400.25 | 4933.5 | - | - |  | ü | - | 2466.75
West Bradford: Clayton Option |  | B120 | B121 | 252 | - | 252 | m |  | - 3m wide traffic free route | Private land - current footpath |  |  | ü | [6 empty] | - Land in private ownership. -Current RoW passes very close to private garden. Realignment of the footpath to the proposed route is likely to be required to facilitate widening and upgrading status. | [5 empty] | X | [27 empty] | 155 | 39060 | - |  | ü | ü | 5859 | 3906 | - | - |  | ü | - | 1953
West Bradford: Clayton Option |  |  |  |  | - | 252 | m |  | - Trotting strip | [23 empty] | X | [20 empty] | 40 | 10080 | - |  | ü | ü | 1512 | 1008 | - | - |  | ü | - | 504
West Bradford: Clayton Option |  |  |  |  | - | 504 | m |  | - Fencing both sides | [25 empty] | X | [18 empty] | 36 | 18144 | - |  | ü | ü | 2721.6 | 1814.4 | - | - |  | ü | - | 907.2
West Bradford: Clayton Option |  | B121 | B122 | 60 | 2.5 | 150 | m² |  | - Existing track/highway resurfaced. | Private land - current footpath | [9 empty] | - Route passes through private land. - Existing RoW has been unofficially diverted. Opportunity to formalise diversion as part of widening and upgrading status. | [13 empty] | X | [19 empty] | 65 | 9750 | - |  | ü | ü | 1462.5 | 975 | - | - |  | ü | - | 487.5
West Bradford: Clayton Option |  | B122 | B123 | 382 | - | 382 | m |  | - 3m wide traffic free route | Private land - current footpath |  |  | ü | [6 empty] | - Land in private ownership. -Current RoW passes through private garden at western end. Realignment of the footpath to the proposed route is suggested to facilitate widening and upgrading status. | [5 empty] | X | [27 empty] | 155 | 59210 | - |  | ü | ü | 8881.5 | 5921 | - | - |  | ü | - | 2960.5
West Bradford: Clayton Option | [5 empty] | 382 | m |  | - Trotting strip | [23 empty] | X | [20 empty] | 40 | 15280 | - |  | ü | ü | 2292 | 1528 | - | - |  | ü | - | 764
West Bradford: Clayton Option | [5 empty] | 382 | m |  | - Fencing one side (382m) | [25 empty] | X | [18 empty] | 36 | 13752 | - |  | ü | ü | 2062.8 | 1375.2 | - | - |  | ü | - | 687.6
West Bradford: Thornton Option |  | B201 | B205 | 6923 | - | - | - |  | - Provision developed by others | Public highway |  |  | ü | [6 empty] | - Provision as described in TCF - Thornton Road Scheme. - Delivery and quality dependent on third party. - Opportunity for continuous footway across side roads for length of Thornton Road. - Risk that identified pinch points reduce standard of overall link. Minimum segregated cycle track required along whole link due to volume and nature of traffic environment on Thornton Road. | [33 empty] | 0 | - | - |  |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K101 | K104 | 864 | - | 1 | No |  | - Cycling in mixed traffic environment | Public highway | 30 |  | ü |  | ü |  | ü | ü |  | - Cobbled surface unlikely to be comfortable for all users. Minimum width required to be re-laid to provide smooth surface. - Northern end of scheme interfaces with proposals for Sustrans Cavendish Street scheme. Schemes to be reviewed and potential for programme/cost implications is incompatible. - Area through industrial estate may not be attractive to all users. Challenge to separate LGV from users. - Assumed volume of traffic low after filters in place. May require additional measures if volumes higher than anticipated. - Proposed filtering of Park Wood Road likely to generate public opposition with risks to programme and costs. - Opportunity to provide improved environment and air quality outside residences and primary school. | [30 empty] | X |  | 209000 | 0 | 209000 | - | Formalise on-street parking on one side by creating a wider footway that can be parked on. This will narrow the carriageway and reduce traffic speeds. |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K101 | K101 | - | - | 1 | No |  | - 1 No. Modal Filter on Low Mill Lane | Public highway | 30 | [24 empty] | X | [17 empty] | 18750 | 18750 | - |  |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K103 | K103 | - | - | 1 | No |  | - 1 No. Bus Gate on Parkwood Street | Public highway | 30 | [27 empty] | X | [14 empty] | 105000 | 105000 | - |  |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K104 | K104 | - | - | 1 | No |  | - Reduced corner radii on junction between Parkwood Street and Park Lane improved | Public highway | 30 | [38 empty] | X |  |  | 10000 | 0 | 10000 | - | £5,000 per corner radii reduction. |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K104 | K105 | 310 | - | 310 | m |  | - Kerb line on eastern side of Park Lane build out to create a 3m wide shared use space | Public highway | 30 |  |  |  |  | ü | ü | ü | ü | - Shared use provision in urban area not ideal under LTN1/20, as higher volumes of pedestrians may be encountered. Insufficient highway widths to provide separated infrastructure. However, provision ensures continuity of overall route. - Some users may find the shared provision at this location unattractive and uncomfortable. Furthermore, some users may perceive the infrastructure to be unsafe. | [19 empty] | X | [13 empty] | 242 | 75020 | - |  |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K105 | K105 | - | - | 1 | No |  | - Junction between Park Lane and Hainworth Wood Road North rationalised to reduce corner radii, reduce traffic speeds and reduce crossing distances. Kerb lines build out. - 1 No. Parallel crossing across Park Lane to provide access to shared use footway. | Public highway | - | [38 empty] | X |  |  | 20950 | 0 | 20950 | - | £5,000 per corner radii reduction and uncontrolled crossing at £10,950. |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K105 | K106 | 350 | - | 350 | m |  | - Cycling in mixed traffic environment - Improved traffic calming measures may be required | Public highway | 20 | [8 empty] | - Residential but traffic volumes unknown. Greater intervention may be required where volumes are higher than expected. - Mixed traffic environments can be perceived to be unsafe and unattractive by some users unless vehicle speeds and volumes are suitable for this approach. | [11 empty] | X | [21 empty] | 295 | 103250 | - |  |  |  | - | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K106 | K107 | 137 | 6 | 822 | m² |  | - Hainworth Road - resurface existing tarmac (approx. 4.5-7.5m wide) | Part-adopted highway |  |  | ü | [6 empty] | - Two local plan development sites are located along Hainworth Road. Both are council owned. Opportunity to integrate development with route planning. Risk that access requirements to new development conflict with proposed route. | [13 empty] | X | [19 empty] | 65 | 53430 | - |  | ü |  | 8014.5 | - | - | - |  | ü | - | 2671.5
Keighley to Cullingworth |  | K107 | K108 | 544 | - | 544 | m |  | -3m traffic free - TRO to close road to through traffic/declassify as road (see below line for new modal filters) | Part-adopted highway |  |  | ü |  |  |  | ü | ü | ü | - Known ecological constraints will require full survey and likely mitigation - Requirement to alter road status and adoption of highway - proposed development site at north end of route may require access from route - Gradient (8-10%) exceeds recommended maximum, but is present on an existing route - Potentially width available for 4.5m shared + trotting strip, but constriction near proposed modal filter. | [5 empty] | X | [27 empty] | 155 | 84320 | - |  | ü |  | 12648 | - | - | - |  | ü | - | 4216
Keighley to Cullingworth | [5 empty] | 544 | m |  | - Trotting strip | [23 empty] | X | [20 empty] | 40 | 21760 | - |  | ü |  | 3264 | - | - | - |  | ü | - | 1088
Keighley to Cullingworth |  | K107a |  | - | - | 1 | No |  | - Modal filter | Part-adopted highway |  |  | ü | [6 empty] | - Installation of modal filters can present a number of stakeholder / community engagement challenges. More specifically, they can be divisive schemes to implement. | [15 empty] | X | [17 empty] | 18750 | 18750 | - |  | ü |  | 2812.5 | - | - | - |  | ü | - | 937.5
Keighley to Cullingworth |  | K108 | K109 | 131 | 7 | 917 | m² |  | - Hainworth Road (south) Resurface (4.5-10m wide) | Part-adopted highway | [23 empty] | X | [19 empty] | 65 | 59605 | - |  | ü |  | 8940.75 | - | - | - |  | ü | - | 2980.25
Keighley to Cullingworth |  | K109 | K110 | 422 | - | 422 | m |  | - Cycling in mixed traffic environment | Public highway | 30 | [5 empty] | ü | ü | ü | - Gradient at northern junction is steep. Challenges for users. - Cobbles present at northern end of route - may require relaying to provide smooth surface. - Opportunity for future access through fields to exclude cycling in mixed traffic section. - Traffic volumes unknown - may require additional provision with programme and cost implications. | [11 empty] | X | [21 empty] | 295 | 124490 | - |  | ü |  | 18673.5 | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K110 | K111 | 105 | 3.5 | 367.5 | m² |  | - Moor Bottom Lane - resurfacing existing tarmac / poor condition (2.5-4.5m wide approx.) | Public highway | [6 empty] | ü | ü | ü | - Gradient (14%) exceeds recommended maximum. Route is existing highway. | [13 empty] | X | [19 empty] | 65 | 23887.5 | - |  | ü |  | 3583.125 | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K111 | K112 | 1360 | - | 1360 | m |  | - 3m traffic free route | Footpath |  | ü | [7 empty] | - requires upgrading from footpath to bridleway - known ecological constraints will require full survey and likely mitigation. - known ecological constraints likely to limit available width for path without compensation - access for construction likely to be challenging - may have implications on construction methods and costs and programme | [5 empty] | X | [27 empty] | 155 | 210800 | - |  | ü |  | 31620 | - | - | - |  | ü | - | 10540
Keighley to Cullingworth | [5 empty] | 966 | m |  | - Fencing east side (966m) | Footpath | [24 empty] | X | [18 empty] | 36 | 34776 | - |  | ü |  | 5216.4 | - | - | - |  | ü | - | 1738.8
Keighley to Cullingworth |  | K112 | K114 | 454 | - | 454 | m |  | - Cycling in mixed traffic environment - extension of 20mph zone on Bingley Road to east to include approach to junction with off road route. - remove on street parking provision around BR/BV junction to ensure visibility | Public highway | 60 |  |  | ü | [5 empty] | - Traffic volumes assumed low - Interrupted bridleway provision - Opportunity to improve traffic calming at entrance to cross roads | [11 empty] | X | [21 empty] | 295 | 133930 | - |  | ü |  | 20089.5 | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K114 | K115 | 825 | 3.5 | 2887.5 | m² |  | - Resurfacing existing farm access, approx. 3-3.5m wide - Will be 'mixed traffic environment' with expected low traffic volume | Bridleway | [6 empty] | ü | ü | ü | - Existing Bridleway - gradients steep in places, average 1:10 for approx. 400m stretch at east end; 1:14 in west half. Existing road. | [13 empty] | X | [19 empty] | 65 | 187687.5 | - |  | ü | ü | 28153.125 | 18768.75 | - | - |  | ü | - | 9384.375
Keighley to Cullingworth |  | K115 | K116 | 538 | - | 538 | m |  | - 3m wide traffic free route | Private land - bridleway |  | ü |  |  |  |  | ü | ü | ü | - Existing Bridleway - Route passes through private land. Ownership unknown - Known historic access issues - attempts to downgrade route to footpath - Route passes bodies of water - full ecological assessment would be required. - Gradient mostly OK, approaching 1:10 for short stretches. Short section of pinch points (2-3m width) between walls. | [5 empty] | X | [27 empty] | 155 | 83390 | - |  | ü | ü | 12508.5 | 8339 | - | - |  | ü | - | 4169.5
Keighley to Cullingworth |  | K116 | K119 | 748 | 4 | 2992 | m² |  | - Resurfacing existing track/road | Private land - no current RoW (K116-117). Bridleway (K117-118). Un-adopted highway (K118-119). |  |  | ü | [6 empty] | - Route passes along private track (K116-K117). Ownership unknown and not visited. - K117-K119 is wide, 5m+. - Assumed low traffic volumes on Station Road. | [13 empty] | X | [19 empty] | 65 | 194480 | - |  | ü | ü | 29172 | 19448 | - | - |  | ü | - | 9724
Keighley to Cullingworth |  | K118 | - | 7 | 5 | 35 | m² |  | - Crossing of Station Road. Low traffic flow is expected (farm track). -Resurfacing req. | Public highway | 30 | [8 empty] | - Low visibility approaching crossing from Turf Lane due to large wall blocking view eastwards. Warning signage req. Low traffic flow expected. | [13 empty] | X | [19 empty] | 65 | 2275 | - |  | ü |  | 341.25 | - | - | - |  |  | - | -
Keighley to Cullingworth |  |  |  | - | - | 1 | No |  | - Potential for User Priority crossing or uncontrolled crossing. Signage. | Public highway | 30 | [8 empty] | - Low visibility approaching crossing from Turf Lane due to large wall blocking view eastwards. Warning signage req. Low traffic flow expected. | X | [32 empty] | 10950 | 10950 | - |  | ü |  | 1642.5 | - | - | - |  |  | - | -
Keighley to Cullingworth |  | K119 | K120 | 230 | - | - | - |  | - Provision developed by others | Private land - no current RoW | [9 empty] | - provision forms part of existing planning permission for development. - Delivery standard dependent on third party | [33 empty] | 0 | - | - |  |  |  | - | - | - | - |  |  | - | -
Cullingworth to Queensbury |  | K120 | K124 | 1193 | - | 1066 | m |  | - Existing traffic free NCN, currently 2-3m in most places. - Widen where possible and/or provide adjacent trotting strip where possible. (Widen by 1 to 2m) Length excludes Hewenden Viaduct and Cullingworth Viaduct - Replace gates & barriers with 1.5m spaced bollards at approx. 5 locations. - Improve signing (e.g. at approach to farm track crossing). | Private land - no current RoW (majority Sustrans) | [9 empty] | - Existing NCN. - Some tree loss expected especially if widening more than 1m. - K122-K123 (315m) is Hewenden Viaduct - no obvious improvements required other then removal of barrier at south end. | [20 empty] | X | [12 empty] | 175 | 186550 | - |  | ü |  | 27982.5 | - | - | - |  | ü | - | 9327.5
Cullingworth to Queensbury |  | K124 | K125 | 225 | - | 225 | m |  | - 3m wide traffic free shared route. Across hill side slope - hence limited width | Private land - bridleway | [9 empty] | - Route passes through private land. Ownerships known. Previously negotiation. - required upgrading to bridleway. Upgrade request already in pace. | [22 empty] | X | [10 empty] | 510 | 114750 | - |  | ü | ü | 17212.5 | 11475 | - | - |  | ü | - | 5737.5
Cullingworth to Queensbury | [5 empty] | 225 | m |  | - Fencing (225m) west side for safety | Private land - bridleway | [24 empty] | X | [18 empty] | 36 | 8100 | - |  | ü | ü | 1215 | 810 | - | - |  | ü | - | 405
Cullingworth to Queensbury |  | K125 | K126 | 65 | - | 65 | m |  | - 3m wide traffic free shared route through woodlands (existing track, width limited to 3m to avoid tree loss) | Footpath subject to current upgrade request. |  |  | ü | [6 empty] | - Land in private ownership. Ownership known with previous engagement having taken place. - Upgrade request is separate to negotiation. | [5 empty] | X | [27 empty] | 155 | 10075 | - |  | ü | ü | 1511.25 | 1007.5 | - | - |  | ü | - | 503.75
Cullingworth to Queensbury | [5 empty] | 65 | m |  | - Fencing (65m) for safety | [25 empty] | X | [18 empty] | 36 | 2340 | - |  | ü | ü | 351 | 234 | - | - |  | ü | - | 117
Cullingworth to Queensbury |  | K126 | K127 | 138 | 2.5 | 345 |  |  | - Use of existing driveway to property - resurface | Footpath subject to current upgrade request. |  |  | ü | [6 empty] | - PRoW footpath status requires upgrading to bridleway. | [13 empty] | X | [19 empty] | 65 | 22425 | - |  | ü | ü | 3363.75 | 2242.5 | - | - |  | ü | - | 1121.25
Cullingworth to Queensbury |  | K127 | K128 | 122 | - | 122 | m |  | Route access ramp, 3m wide shared traffic free. - Approx. 120m long for 1:20 grad. Tree loss expected; flat embankment at top is fairly clear of trees. | Private land - no current RoW (Sustrans) |  | ü | [7 empty] | - Earthworks required. - Sustrans/RPL own part/all of old rail land. - Shared use path would ramp up from north end. - PRoW footpath located along lower edge of embankment but is narrow. - Note steep embankment for construction purposes - may require hand construction | [21 empty] | X | [11 empty] | 1525 | 186050 | - |  | ü | ü | 27907.5 | 18605 | - | - |  | ü | - | 9302.5
Cullingworth to Queensbury | [5 empty] | 244 | m |  | - Fencing on both side of traffic-free path. | [25 empty] | X | [18 empty] | 36 | 8784 | - |  | ü | ü | 1317.6 | 878.4 | - | - |  | ü | - | 439.2
Cullingworth to Queensbury |  | K128 | K130 | 678 | - | 678 | m |  | - 3m wide traffic free route | Private land - no current RoW (Sustrans to K129) | [9 empty] | - Route passes through private land (south half) - unvisited. Ownership known - Route previously subject to planning permission now lapsed - Ecological assessment required and mitigation and compensation likely to be required. | [5 empty] | X | [27 empty] | 155 | 105090 | - |  | ü | ü | 15763.5 | 10509 | - | - |  | ü | - | 5254.5
Cullingworth to Queensbury | [5 empty] | 678 | m |  | - Trotting strip with some tree loss expected at north end (80m stretch). Central 218m utilises existing PRoW path along quarry track (good width). 380m at south end is on unexplored private land, looks reasonably clear of trees in places. | [23 empty] | X | [20 empty] | 40 | 27120 | - |  | ü | ü | 4068 | 2712 | - | - |  | ü | - | 1356
Cullingworth to Queensbury |  | K129a |  | - | - | 1 | No |  | - Inspection and any required works to over-bridge (over road) - blocked off above, condition unknown. | Private land - no current RoW (RPL) |  | ü | [7 empty] | - Structural assessment may reveal need for unforeseen works to overbridge. | [31 empty] | X | 5500 | 0 | - | 5500 | Annual inspection at £500. Condition of structure unknown but assumed up to £5,000 of repair work required. | ü | ü | - | - | 825 | 550 |  | ü | - | 275
Cullingworth to Queensbury |  | K130 | K130a | 385 | - | 385 | m |  | - Route access ramp, earthworks expected. - Along edge of woodland area, within railway land but ownership unknown. - Links to Foster Park View. | Private land - no current RoW. Footpath for approx. 100m at parallel northern end. |  | ü | [7 empty] | - Route across private land. Ownership unknown. -Inaccessible and unvisited. - Route likely to require ecological mitigation. - Potential link to Denholme and Doe Park Water Activity Centre, though Foster Park View is steep. | [21 empty] | X | [11 empty] | 1525 | 587125 | - |  | ü | ü | 88068.75 | 58712.5 | - | - |  | ü | - | 29356.25
Cullingworth to Queensbury |  |  |  |  | - | 385 | m |  | - Fencing on west side only | [25 empty] | X | [18 empty] | 36 | 13860 | - |  | ü | ü | 2079 | 1386 | - | - |  | ü | - | 693
Cullingworth to Queensbury |  | K130 | K137 | 330 | - | 330 | m |  | - 4.5m wide traffic free route between inverted arches / tunnels, total length shown. - Four sections of lengths 112m, 70m, 34.5m & 114.5m. | Private land - no current RoW |  | ü |  |  |  | ü |  |  |  | - Appears to be woodland in areas, possibly dense - Assumed suitable regarding width and gradient due to prior rail status - Inaccessible and unvisited - Land ownership details not known. - Known ecological risk - tunnels and high quality land required full ecological assessment and likely mitigation and compensation. - Condition of tunnels last known to be good, but risk of deterioration and associate costs and programme implications. - Works in confined spaces may present construction challenges. - Safety - unlikely to be area used at night unless adequate lighting is provided. - Land ownership | [26 empty] | X | [6 empty] | 240 | 79200 | - |  | ü | ü | 11880 | 7920 | - | - |  | ü | - | 3960
Cullingworth to Queensbury |  |  |  | 230 | - | 230 | m |  | - Provision of 4.5m wide traffic-free route through structures (total length through structures is shown) | [37 empty] | X | [6 empty] | 240 | 55200 | - |  | ü | ü | 8280 | 5520 | - | - | ü |  | 276 | -
Cullingworth to Queensbury |  |  |  | 230 | - | 230 | m |  | - Structural check and improvements to inverted arches/ short tunnels: 2 inverted arches (70m & 30m long) and 1 tunnel (130m long - Doe Park Tunnel) | [36 empty] | X | [7 empty] | 1766 | - | 406180 |  | ü | ü | - | - | 60927 | 40618 | ü |  | 2030.9 | -
Cullingworth to Queensbury |  |  |  | 230 | - | 6 | No |  | - Security: Motion detected CCTV and secure gates at each tunnel portal | [35 empty] | X | [8 empty] | 20000 | 120000 | - |  | ü | ü | 18000 | 12000 | - | - | ü |  | 600 | -
Cullingworth to Queensbury |  |  |  | 200 | - | 200 | m |  | - Lighting through tunnel (and longest inverted arch) | [28 empty] | X | [15 empty] | 50 | 10000 | - |  | ü | ü | 1500 | 1000 | - | - | ü |  | 50 | -
Cullingworth to Queensbury |  | K137 | K138 | 300 | - | - | - |  | - Provision to be developed by others | Private land - no current RoW | [9 empty] | - Provision forms part of existing planning permission for development. - Delivery standard dependent on third party - 3-4m shared cycling and walking path | [33 empty] | 0 | - | - |  |  |  | - | - | - | - |  |  | - | -
Cullingworth to Queensbury |  | K138 | K141 | 485 | - | 485 | m |  | - 4.5m wide traffic free route either side of Hamers Hill Tunnel, total length shown - Two sections of lengths 75m & 410m | Private land - no current RoW | [9 empty] | - Appears to be woodland in areas, possibly dense - Assumed suitable regarding width and gradient due to prior rail status - Inaccessible and unvisited - Land ownership details not known. | [26 empty] | X | [6 empty] | 240 | 116400 | - |  | ü | ü | 17460 | 11640 | - | - |  | ü | - | 5820
Cullingworth to Queensbury |  |  |  | 135 | - | 135 | m |  | - Structural check and improvements to Hamers Hill Tunnel (135m long) |  |  | ü |  |  |  | ü |  |  |  | - Works in confined spaces may present construction challenges. - Ownership of tunnel is part private part HSE. Likely to require negotiation and ownership transfer - Safety - unlikely to be used at night | [25 empty] | X | [7 empty] | 1766 | - | 238410 |  | ü | ü | - | - | 35761.5 | 23841 | ü |  | 1192.05 | -
Cullingworth to Queensbury |  |  |  | 135 | - | 135 | m |  | - Provision of 4.5m wide traffic-free route through tunnel (approximate length shown) | [6 empty] | ü |  |  |  | - Known ecological risk - tunnels and high quality land required full ecological assessment t and likely mitigation and compensation. - Condition of tunnels last known to be good, but risk of deterioration and associated costs and programme implications. - Lighting requirements? - Works in confined spaces may present construction challenges. - Safety - unlikely to be area used at night - Ownerships unknown. | [26 empty] | X | [6 empty] | 240 | 32400 | - |  | ü | ü | 4860 | 3240 | - | - | ü |  | 162 | -
Cullingworth to Queensbury |  |  |  | 135 | - | 2 | No |  | - Security: Motion detected CCTV and secure gates at each tunnel portal | [35 empty] | X | [8 empty] | 20000 | 40000 | - |  | ü | ü | 6000 | 4000 | - | - | ü |  | 200 | -
Cullingworth to Queensbury |  |  |  | 135 | - | 135 | m |  | - Lighting through tunnel | [28 empty] | X | [15 empty] | 50 | 6750 | - |  | ü | ü | 1012.5 | 675 | - | - | ü |  | 33.75 | -
Cullingworth to Queensbury |  | K141 | K142 | 605 | - | 605 | m |  | - Provision of 4.5m wide traffic-free route through tunnel | Private land - no current RoW |  | ü |  |  |  | ü |  |  |  | - Well Head tunnel. Condition last examined to be fair. Survey required and may have implications on programme and cost - Works in confined spaces may present construction challenges. - Ownership of tunnel is part private part HSE. Likely to require negotiation and ownership transfer - Safety - unlikely to be used at night | [26 empty] | X | [6 empty] | 240 | 145200 | - |  | ü | ü | 21780 | 14520 | - | - | ü |  | 726 | -
Cullingworth to Queensbury |  | K141 | K142 | 605 | - | 605 | m |  | - Structural check and improvements to Well Head Tunnel | [36 empty] | X | [7 empty] | 1766 | - | 1068430 |  | ü | ü | - | - | 160264.5 | 106843 | ü |  | 5342.15 | -
Cullingworth to Queensbury |  | K141 | K142 | 605 | - | 3 | No |  | - Security: Motion detected CCTV and secure gates at each tunnel portal | [35 empty] | X | [8 empty] | 20000 | 60000 | - |  | ü | ü | 9000 | 6000 | - | - | ü |  | 300 | -
Cullingworth to Queensbury |  | K141 | K142 | 605 | - | 605 | m |  | - Lighting through tunnel | [28 empty] | X | [15 empty] | 50 | 30250 | - |  | ü | ü | 4537.5 | 3025 | - | - | ü |  | 151.25 | -
Cullingworth to Queensbury |  | K142 | K143 | 635 | - | 635 | m |  | - Provision of 4.5m wide traffic free route - Passes below Thornton Road via a bridge, maintained by Bradford Highways Service. | Private land - no current RoW | [9 empty] | - Ownership - not known, agreement required. - Dense woodland along whole stretch - tree felling required - East end would connect to existing NCN. | [6 empty] | X | [26 empty] | 188 | 119380 | - |  | ü | ü | 17907 | 11938 | - | - |  | ü | - | 5969
Cullingworth to Queensbury |  | K142a | K142a | - | - | 1 | No |  | '- Inspection and any required works to under-bridge (under road) - condition unknown. | Private land - no current RoW | [41 empty] | X | 5500 | 0 | - | 5500 | Annual inspection at £500. Condition of structure unknown but assumed up to £5,000 of repair work required. | ü | ü | - | - | 825 | 550 |  | ü | - | 275
Cullingworth to Queensbury |  | K143 | K147 | 2570 | - | 2570 | m |  | - Existing traffic free with improvements . Total length excluding Thornton Viaduct is shown (no visible improvements necessary to viaduct) - Widen where possible | Private land - no current RoW (Sustrans K144 approx. to Headley Lane, Sustrans/RPL cockin Lane to Station Road). Bridleway (Headley Lane to Cockin Lane). Footpath (Brow Lane to Station Road). | [9 empty] | - Existing GNRT. - Opportunity for improvement as part of Thornton Road TCF scheme - Currently average 2-2.5m north of Headley Lane (excluding viaduct) and south of Cockin Lane ; 4m wide for 400m north from Cockin Lane. - Potential to widen in most places (say 2km), some tree loss expected. - At-grade crossings not costed - possible future improvement. | [20 empty] | X | [12 empty] | 175 | 449750 | - |  | ü | ü | 67462.5 | 44975 | - | - |  | ü | - | 22487.5
Cullingworth to Queensbury |  | K144 | B205 | 144 | - | 144 | m |  | - Existing traffic free with improvements (widening). - Land acquisition may be necessary. | Private land - no current RoW | [5 empty] | ü | ü | ü | ü | - Compliance - narrow provision which some users may consider to be unattractive and uncomfortable. Where there are high volumes of pedestrians, some users may also consider this level of provision to be unsafe. As such, future upgrade could be considered where volumes increase significantly. - Limited opportunity for improvement without additional land acquisition | [20 empty] | X | [12 empty] | 175 | 25200 | - |  | ü | ü | 3780 | 2520 | - | - |  | ü | - | 1260
Cullingworth to Queensbury |  | K147 | K148 | 808 | 5.75 | 4646 | m² |  | - Resurfacing | Un-adopted highway | [6 empty] | ü | ü | ü | - Compliance - very steep existing road. 4.5-7m wide. Gradient is 1:10 in places. This may detract some users from this section. It may also be uncomfortable for some users. - Section could be further improvement through the introduction of resting places, feature boards, benches etc. | [13 empty] | X | [19 empty] | 65 | 301990 | - |  | ü | ü | 45298.5 | 30199 | - | - |  | ü | - | 15099.5
Cullingworth to Queensbury |  | K148 | H128 | 116 | - | 116 | m |  | - Cycling in mixed traffic environment | Un-adopted highway | 30 | [8 empty] | - Mixed traffic environments can be perceived to be unsafe and unattractive by some users unless vehicle speeds and volumes are suitable for this approach. However, the volumes of traffic along Station Road are thought to be low enough to create a suitable mixed traffic environment. | [11 empty] | X | [21 empty] | 295 | 34220 | - |  | ü | ü | 5133 | 3422 | - | - |  | ü | - | 1711
Keighley to Cullingworth |  | - | - | - | - | 17 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 3825 | - |  |  |  | - | - | - | - |  |  | - | -
Cullingworth to Queensbury |  | - | - | - | - | 15 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 3375 | - |  |  |  | - | - | - | - |  |  | - | -
West Bradford: Clayton Option |  | - | - | - | - | 22 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 4950 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Greenway Option |  | - | - | - | - | 14 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 3150 | - |  |  |  | - | - | - | - |  |  | - | -
Alpine Option |  | - | - | - | - | 14 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 3150 | - |  |  |  | - | - | - | - |  |  | - | -
Tunnel Option |  | - | - | - | - | 2 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 450 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield: Highway Option |  | - | - | - | - | 13 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 2925 | - |  |  |  | - | - | - | - |  |  | - | -
Halifax to Holmfield |  | - | - | - | - | 4 | No |  | Wayfinding Signage | Varies | [9 empty] | Opportunity to ensure a good level of coherence across all alignments. | [23 empty] | X | [9 empty] | 225 | 900 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
[54 empty] | 0 | 0 | - |  |  |  | - | - | - | - |  |  | - | -
0

## Scheme Costs
|  | Cycling & Walking Infrastructure (Excludes bridge & tunnel structures) | [5 empty] | Bridge and tunnel (structures only, excluding Queensbury Tunnel) | [8 empty] | Queensbury Tunnel
Corridor | Length (m) | Construction Costs (without preliminaries) | Construction Preliminaries @ | Contingency @ | Design & development @ | Ecology costs @ | Land & Legal Costs @ | Construction Costs - without Preliminaries | Construction Preliminaries @ | Contingency @ | Design & development @ | Ecology costs @ | Land & Legal Costs @ | Total Cost | Tunnel Maintenance | Other Maintenance | Queensbury Tunnel Works inc. ventilation | Queensbury Tunnel Contingency | Queensbury Tunnel Design & Development @3% | Total Tunnel Cost | Queensbury Tunnel Maintenance | Total corridor cost (excl. maintenance)
|  |  | 15% | 10% | 8% | 15% | 10% |  | 15% | 10% | 8% | 15% | 10% |  | 0.5% | 5%
Halifax to Holmfield | 1524 | 578335 | 86750 | 66509 | 58528 | 57325 | 32112 | 0 | 0 | 0 | 0 | 0 | 0 | 879559 | 0 | 16056 |  |  |  | 0 |  | 879559
Halifax to Holmfield: Greenway Option | 4225 | 1337740 | 200661 | 153840 | 135379 | 153359 | 101144 | 0 | 0 | 0 | 0 | 0 | 0 | 2082123 | 0 | 50572 |  |  |  | 0 |  | 2082123
Halifax to Holmfield: Highway Option | 5954 | 552360 | 82854 | 63521 | 55899 | 8400 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 768634 | 0 | 2800 |  |  |  | 0 |  | 768634
Alpine Option | 4798 | 2403605 | 360541 | 276415 | 243245 | 282710 | 184723 | 0 | 0 | 0 | 0 | 0 | 0 | 3751239 | 0 | 92362 |  |  |  | 0 |  | 3751239
Tunnel Option | 3082 | 1279226 | 191884 | 147111 | 129458 | 69506 | 46338 | 0 | 0 | 0 | 0 | 0 | 0 | 1863523 | 4077 | 23169 | 21610764 | 4123000 | 648323 | 22259087 | 24090 | 24122610
West Bradford: Clayton Option | 7001 | 2417771 | 362666 | 278044 | 244678 | 197172 | 136522 | 45000 | 6750 | 5175 | 4554 | 6750 | 4500 | 3709582 | 0 | 62050 |  |  |  | 0 |  | 3709582
West Bradford: Thornton Option | 6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
Keighley to Cullingworth | 7025 | 1790326 | 268549 | 205888 | 181181 | 186680 | 46556 | 0 | 0 | 0 | 0 | 0 | 0 | 2679180 | 0 | 47450 |  |  |  | 0 |  | 2679180
Cullingworth to Queensbury | 9172 | 2901584 | 435238 | 333682 | 293640 | 434731 | 271166 | 1724020 | 258603 | 198262 | 174471 | 258603 | 172402 | 7456402 | 11064 | 120470 |  |  |  | 0 |  | 7456402
Corridor | Corridor Length (m) | Most Attractive and Advantageous - Tunnel Option | Most Attractive and Advantageous - Tunnel Option | Most Attractive and Advantageous - Alpine Option | Most Attractive and Advantageous - Alpine Option | Next Preferred - Tunnel Option | Next Preferred - Tunnel Option | Next Preferred - Alpine Option | Next Preferred - Alpine Option | Low Cost Alternative - Tunnel Option | Low Cost Alternative - Tunnel Option | Low Cost Alternative - Alpine Option | Low Cost Alternative - Alpine Option | * To account for inclusion of different alignments in Tunnel or Greenway Uplift case, each route is divided into different columns. The check line at the bottom of the costs should stay Green. If you get a red "NO" it means that the alignments in the route as a whole are not correct.
Usage Uplift Category |  | Tunnel | Greenway | Tunnel (n/a) | Greenway | Tunnel | Greenway | Tunnel (n/a) | Greenway | Tunnel | Greenway | Tunnel (n/a) | Greenway
Halifax to Holmfield | 1524 |  | X |  | X |  | X |  | X |  | X |  | X
Halifax to Holmfield: Greenway Option | 4225 |  | X |  | X |  | X |  | X
Halifax to Holmfield: Highway Option | 5954 |  | X |  | X | [5 empty] | X |  | X
Alpine Option | 4798 |  |  |  | X |  |  |  | X |  |  |  | X
Tunnel Option | 3082 | X |  |  |  | X |  |  |  | X
West Bradford: Clayton Option | 7001 |  | X |  | X |  | X |  | X
West Bradford: Thornton Option | 6923 |  | X |  | X | [5 empty] | X |  | X
Keighley to Cullingworth | 7025 |  | X |  | X |  | X |  | X |  | X |  | X
Cullingworth to Queensbury | 9172 |  | X |  | X |  | X |  | X |  | X |  | X
Option Length (m) |  | 3082 | 41824 | 0 | 46622 | 3082 | 28947 | 0 | 33745 | 3082 | 30598 | 0 | 35396
Costs
Cycling & walking (C&W) infrastructure
Construction (without preliminaries) |  | 1279226 | 9578116 | 0 | 11981721 | 1279226 | 9025756 | 0 | 11429361 | 1279226 | 5822605 | 0 | 8226210
Ecology @ | 15 % | 69506 | 1037667 | 0 | 1320377 | 69506 | 1029267 | 0 | 1311977 | 69506 | 687136 | 0 | 969846
Land & Legal @ | 10 % | 46338 | 593100 | 0 | 777823 | 46338 | 587500 | 0 | 772223 | 46338 | 355434 | 0 | 540157
Construction Preliminaries @ | 15 % | 191884 | 1436718 | 0 | 1797259 | 191884 | 1353864 | 0 | 1714405 | 191884 | 873391 | 0 | 1233932
Contingency @ | 10 % | 147111 | 1101484 | 0 | 1377899 | 147111 | 1037963 | 0 | 1314378 | 147111 | 669600 | 0 | 946015
Design & Development @ | 8 % | 129458 | 969305 | 0 | 1212550 | 129458 | 913406 | 0 | 1156651 | 129458 | 589248 | 0 | 832493
Cycling and Walking Infrastructure Option Cost |  | 1863523 | 14716390 | 0 | 18467629 | 1863523 | 13947756 | 0 | 17698995 | 1863523 | 8997414 | 0 | 12748653
Bridge & Tunnel (Structures only)
Construction (without preliminaries) |  | 0 | 1769020 | 0 | 1769020 | 0 | 1769020 | 0 | 1769020 | 0 | 1724020 | 0 | 1724020
Ecology @ | 15 % | 0 | 265353 | 0 | 265353 | 0 | 265353 | 0 | 265353 | 0 | 258603 | 0 | 258603
Land & Legal @ | 10 % | 0 | 176902 | 0 | 176902 | 0 | 176902 | 0 | 176902 | 0 | 172402 | 0 | 172402
Construction Preliminaries @ | 15 % | 0 | 265353 | 0 | 265353 | 0 | 265353 | 0 | 265353 | 0 | 258603 | 0 | 258603
Contingency @ | 10 % | 0 | 203437 | 0 | 203437 | 0 | 203437 | 0 | 203437 | 0 | 198262 | 0 | 198262
Design & Development @ | 8 % | 0 | 179025 | 0 | 179025 | 0 | 179025 | 0 | 179025 | 0 | 174471 | 0 | 174471
Bridge & Tunnel Structures option cost |  | 0 | 2859090 | 0 | 2859090 | 0 | 2859090 | 0 | 2859090 | 0 | 2786361 | 0 | 2786361
Queensbury Tunnel Construction | 0 | 21610764 | 0 | 0 | 0 | 21610764 | 0 | 0 | 0 | 21610764 | 0 | 0 | 0
Queensbury Tunnel Contingency | 0 | 4123000 | 0 | 0 | 0 | 4123000 | 0 | 0 | 0 | 4123000 | 0 | 0 | 0 | Agreed remove and replace with 66% OB
Queensbury Tunnel Design & Development | 0 | 648323 | 0 | 0 | 0 | 648323 | 0 | 0 | 0 | 648323 | 0 | 0 | 0
Queensbury Tunnel Option Cost | 0 | 22259087 | 0 | 0 | 0 | 22259087 | 0 | 0 | 0 | 22259087 | 0 | 0 | 0
Total Option Cost | 0 | 24122610 | 17575480 | 0 | 21326719 | 24122610 | 16806846 | 0 | 20558085 | 24122610 | 11783775 | 0 | 15535014
Check composite total matches |  |  | Yes |  | Yes |  | Yes |  | Yes |  | Yes |  | Yes
Optimism Bias applied to inflated & varied costs | Applied to
Optimism Bias (C&W infrstructure) | C&W Infrastructure | 857220.58 | 6769539.4 | 0 | 8495109.34 | 857220.58 | 6415967.76 | 0 | 8141537.7 | 857220.58 | 4138810.44 | 0 | 5864380.38
Optimism Bias (Bridge & Tunnel) | Structures only | 0 | 1572499.5 | 0 | 1572499.5 | 0 | 1572499.5 | 0 | 1572499.5 | 0 | 1532498.55 | 0 | 1532498.55
Optimism Bias (Queensbury Tunnel) | Queensbury Tunnel | 14690997.42 | 0 | 0 | 0 | 14690997.42 | 0 | 0 | 0 | 14690997.42 | 0 | 0 | 0
Total cost including OB |  | 39670828 | 25917518.9 | 0 | 31394327.84 | 39670828 | 24795313.26 | 0 | 30272122.2 | 39670828 | 17455083.99 | 0 | 22931892.93
Calculated Optimism Bias for AMAT |  | 64.45% | 47.46% | N/A | 47.21% | 64.45% | 47.53% | N/A | 47.25% | 64.45% | 48.13% | N/A | 47.61%
Queensbury Tunnel maintenance per year |  | 24090 | 0 | 0 | 0 | 24090 | 0 | 0 | 0 | 24090 | 0 | 0 | 0
Other tunnel maintenance per year |  | 4077 | 11064 | 0 | 11064 | 4077 | 11064 | 0 | 11064 | 4077 | 11064 | 0 | 11064
C&W infrastructure maintenance per year |  | 23169 | 299398 | 0 | 391760 | 23169 | 296598 | 0 | 388960 | 23169 | 186776 | 0 | 279138
Total maintenance per year |  | 51336 | 310462 | 0 | 402824 | 51336 | 307662 | 0 | 400024 | 51336 | 197840 | 0 | 290202
Agreed OB application | %
C&W infrastructure OB | 46 | Agree remain as draft: Stage 1 Roads (I have updated 44% to 46% in keeping with latest version of TAG
Tunnel & Bridge OB (Non- Queensbury) | 55 | Agree remain as draft: Stage 1 Fixed links
Queensbury Tunnel OB | 66 | Agreed apply 66% OB to tunnel segment

## Uncontrolled crossing
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Uncontrolled Crossing
Construction only rate | 10950
Unit | Number
Specification | 3m wide dropped kerbs on both sides of the carriageway, including a pedestrian refuge island and tactile paving.
Assumptions | - Single carriageway two way road with no physical separation between opposing traffic lanes. - Rate includes for electric works associated with illuminated bollards on refuge island.
Exclusions | - Carriageway / Footway Resurfacing - Improved Street lighting - Diversion or protection of utility apparatus - Highway drainage
Source Information | The rate is a median taken from rates published by two highway authorities in England. The published rates vary between £9,400 and £12,500.
Other comments | Some uncontrolled pedestrian crossing points will not include a refuge island, particularly those implemented on narrower single carriageway roads. These roads may instead use a raised table to provide a crossing point, but also to calm traffic speeds. For the purposes of this cost estimating exercise, this rate will account for crossings that adopt either a refuge island, or a raised table, but not both.

## Controlled Crossing
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Signal controlled crossing (Puffin / Toucan).
Construction only rate | 96500
Unit | Number
Specification | Stand-alone traffic signal controlled pedestrian/cycle crossing
Assumptions | - Single carriageway two way road with no physical separation between opposing traffic lanes. - No existing traffic signal infrastructure - all new
Exclusions | - Carriageway / Footway Resurfacing - Improved Street lighting - Diversion or protection of utility apparatus
Source Information | The rate is a median taken from rates published by two highway authorities in England. The published rates vary between £53,000 and £140,000.
Other comments | Toucan and Pegasus crossings will inevitably result in more signal infrastructure being required. Furthermore, kerbing and civil works are required to accommodate the increased width of a crossing when compared to a puffin. However, the difference in implementation costs between these crossing types is considered to be insignificant at this feasibility stage.

## Controlled Crossing (Separated)
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Signal controlled crossing (Puffin / Toucan / Pegasus) - Dual Carriageway.
Construction only rate | 160000
Unit | Number
Specification | Stand-alone traffic signal controlled pedestrian/cycle crossing
Assumptions | - Dual carriageway road with a central reservation. - No existing traffic signal infrastructure - all new
Exclusions | - Carriageway / Footway Resurfacing - Improved Street lighting - Diversion or protection of utility apparatus
Source Information | The rate has been published by an English highway authority.
Other comments | Toucan and Pegasus crossings will inevitably result in more signal infrastructure being required. Furthermore, kerbing and civil works are required to accommodate the increased width of a crossing when compared to a puffin. However, the difference in implementation costs between these crossing types is considered to be insignificant at this feasibility stage.

## Zebra Crossing
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Zebra / Parallel Crossing
Construction only rate | 28656
Unit | Number
Specification | Zebra / Parallel crossing as per Traffic Signs Regulations and General Directions 2016 and Traffic Signs Manual Chapters 5 & 6
Assumptions | - High friction surface dressing required on approaches. - Beacons included within rate. - Single carriageway two way road with no physical separation between opposing traffic lanes.
Exclusions | - Carriageway / Footway Resurfacing - Raised Tables - Improved Street lighting - Diversion or protection of utility apparatus
Source Information | The rate is a median taken from rates published by two highway authorities in England. The published rates vary between £21,500 and £35,000.
Other comments | Parallel crossings will inevitably result in slightly more road markings and civils works, such as kerbing, being required. However, the difference in cost is not considered significant enough to separate the costs for these two interventions at this stage.

## Zebra Crossing (Separated)
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Zebra / Parallel Crossing (Separated Carriageway)
Construction only rate | 41500
Unit | Number
Specification | Zebra / Parallel crossing as per Traffic Signs Regulations and General Directions 2016 and Traffic Signs Manual Chapters 5 & 6
Assumptions | - High friction surface dressing required on approaches. - Beacons included within rate. - Dual carriageway two way road with separation in the form of a traffic island or central reservation.
Exclusions | - Carriageway / Footway Resurfacing - Raised Tables - Improved Street lighting - Diversion or protection of utility apparatus
Source Information | The rate is a median taken from rates published by two highway authorities in England. The published rates vary between £29,500 and £65,000.
Other comments | Parallel crossings will inevitably result in slightly more road markings and civils works, such as kerbing, being required. However, the difference in cost is not considered significant enough to separate the costs for these two interventions at this stage.

## 3m Wide Shared Path
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 3m wide Traffic-free Route (shared path).
Construction only rate | 155
Unit | Per linear metre
Specification | 150mm sub base with a single layer of 60mm thickness of AC14 (asphalt concrete with a 14mm stone size). Path to have 2.5% crossfall. 300 x 300mm french drain alongside path on one side.
Assumptions | - Flat ground - No major earthworks required - No retaining structures - Sub base will extend beyond the width of the path to provide sufficient edge support in lieu of a kerbed edge or channel. - Traffic loading not required.
Exclusions | - Kerbing and edgings - Fencing - Landscaping - Structures - Diversion or protection of utility apparatus
Source Information | The rate is a median taken from 13 tender responses to three Sustrans projects from 2019/20. The lowest tendered rate was £59, with the most expensive rate being £238.
Other comments | An alternative specification would be to use two-layers of bituminous surfacing comprising a lower layer of a coarser bituminous material: 60mm thickness of AC20 (asphalt concrete with a 20mm stone size) overlaid by a thinner surface course: 20mm thickness of AC10 (10mm stone size). This would provide a superior riding surface that may offer increased comfort to certain users. I.e., those using wheelchairs and adapted bikes. This specification would likely result in an increase in costs.

## 4.5m Wide Shared Path
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 4.5m wide Traffic-free Route (shared path).
Construction only rate | 188
Unit | Per linear metre
Specification | 150mm sub base with a single layer of 60mm thickness of AC14 (asphalt concrete with a 14mm stone size). Path to have 2.5% crossfall. 300 x 300mm french drain alongside path on one side.
Assumptions | - Flat ground - No major earthworks required - No retaining structures - Sub base will extend beyond the width of the path to provide sufficient edge support in lieu of a kerbed edge or channel. - Traffic loading not required.
Exclusions | - Kerbing and edgings - Fencing - Landscaping - Structures - Diversion or protection of utility apparatus
Source Information | The rate is taken from 'Paths for All: Estimating price guide for path projects (2019)'. The rate provided for a square metre of path is between £24.80 and £42, with an average of £33.40. The upper rate has been used for the purposes of this cost estimate, as this achieves consistency with the rate used for the 3m wide shared path.
Other comments | An alternative specification would be to use two-layers of bituminous surfacing comprising a lower layer of a coarser bituminous material: 60mm thickness of AC20 (asphalt concrete with a 20mm stone size) overlaid by a thinner surface course: 20mm thickness of AC10 (10mm stone size). This would provide a superior riding surface that may offer increased comfort to certain users. I.e., those using wheelchairs and adapted bikes. This specification would likely result in an increase in costs.

## 5m Wide Shared Path
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 5m wide Traffic-free Route (shared path).
Construction only rate | 230
Unit | Per linear metre
Specification | 150mm sub base with a single layer of 60mm thickness of AC14 (asphalt concrete with a 14mm stone size). Path to have 2.5% crossfall. 300 x 300mm french drain alongside path on one side.
Assumptions | - Flat ground - No major earthworks required - No retaining structures - Sub base will extend beyond the width of the path to provide sufficient edge support in lieu of a kerbed edge or channel. - Traffic loading not required.
Exclusions | - Kerbing and edgings - Fencing - Landscaping - Structures - Diversion or protection of utility apparatus
Source Information | This rate is based upon '4m wide Traffic-free Route (shared path)', which has been increased proportionately to account for the additional metre of width.
Other comments | An alternative specification would be to use two-layers of bituminous surfacing comprising a lower layer of a coarser bituminous material: 60mm thickness of AC20 (asphalt concrete with a 20mm stone size) overlaid by a thinner surface course: 20mm thickness of AC10 (10mm stone size). This would provide a superior riding surface that may offer increased comfort to certain users. I.e., those using wheelchairs and adapted bikes. This specification would likely result in an increase in costs.

## One-way light Seperated Tracks
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Separated Cycle Track (On-Road)
Construction only rate | 120
Unit | Per linear metre
Specification | 1.5m wide lightly separated cycle track (one-way).
Assumptions | - Traffic speed and volumes considered suitable for light separation. - Separation takes the form of a reflective vertical post bolted to the carriageway surface. - Rate includes a cycle track on both sides of the road. - Includes all road markings and signage required by the Traffic Signs Regulations and General Directions 2016 and the Traffic Signs Manual.
Exclusions | - Does not include treatments / interventions at junctions - Street lighting improvements - Temporary Traffic Management - Traffic Regulation Orders and legal costs
Source Information | Department for Transport - Typical Costs of Cycling Interventions: January 2017.
Other comments | Separated cycle tracks can take a number of forms. For roads that experience higher traffic volumes and speeds, kerb or level separation may be required.

## Bi directional Kerb Separated
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Bi-Directional Kerb Separated Track (On-Road)
Construction only rate | 450
Unit | Per linear metre
Specification | 3m wide kerb separated cycle track (two-way)
Assumptions | - Traffic speed and volumes considered suitable for kerb separation. - Separation takes the form of a kerbed upstand and / or level difference.
Exclusions | - Treatments / interventions at junctions - Road markings and signage required by the Traffic Signs Regulations and General Directions 2016 and the Traffic Signs Manual. - Changes to highway drainage and road markings / signage. Temporary Traffic Management
Source Information | Department for Transport - Typical Costs of Cycling Interventions: January 2017.
Other comments | Separated cycle tracks can take a number of forms. For roads that experience lower traffic volumes and speeds, light seperation may be suffcient.

## One-way Kerb Separated
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | One-way Kerb Seperated Track (On-Road)
Construction only rate | 355
Unit | Per linear metre
Specification | 1.5m wide kerb separated cycle track
Assumptions | - Traffic speed and volumes considered suitable for kerb separation. - Separation takes the form of a kerbed upstand and / or level difference.
Exclusions | - Treatments / interventions at junctions - Road markings and signage required by the Traffic Signs Regulations and General Directions 2016 and the Traffic Signs Manual. - Changes to highway drainage and road markings / signage. Temporary Traffic Management
Source Information | Department for Transport - Typical Costs of Cycling Interventions: January 2017.
Other comments | Separated cycle tracks can take a number of forms. For roads that experience lower traffic volumes and speeds, light seperation may be suffcient.

## Mixed Traffic Environment
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Mixed traffic Environment
Construction only rate | 295
Unit | Per linear metre
Specification | Combination of vertical and horizontal traffic calming measures as required.
Assumptions | -Assumes set of double speed cushions every 40m and some horizontal deflection (buildouts) to create an overall narrower street. - Includes road markings and signage - Includes changes to street lighting where required - Includes minor modifications to highway drainage
Exclusions | - Temporary Traffic Management - Legal and advertising costs associated with Traffic Regulation Orders.
Source Information | The rate is a median taken from rates published by two highway authorities in England. The published rates vary between £205 and £295 per metre.
Other comments | Traffic calming can take many forms, all of which will come with different costs. For some streets, simple measures such as centreline removal may suffice in managing traffic speeds. As such, further investigation will be required to understand the specific needs of each mixed traffic environment in order to arrive at a more accurate costing.

## Trotting Strip
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 2m wide Trotting Strip (Equestrian use only).
Construction only rate | 40
Unit | Per linear metre
Specification | 200mm compacted Type 1 sub-base at least 50mm above the existing ground level. 25mm topsoil added to the compacted layer of sub base and then mixed. Sub-base / topsoil mixture then seeded with a wear resistant grass and lightly rolled.
Assumptions | - Arising's from adjacent path cannot be used to form the topsoil layer. - Ground conditions are suitable and a geotextile layer is not required. - Soil conditions are suitable for horse loading, i.e. soils aren't clay heavy. - Drainage is adequate
Exclusions | - Geotextile - Ground stabilisation - Drainage - Fencing - Path for other users (i.e. Cyclists and pedestrians) - Diversion or protection of utility apparatus
Source Information | The rate has been developed using earthworks and material rates provided through a tender process for a number of DfT funded Sustrans projects in 2019/2020. The specification has been developed in accordance with the British Horse Society's guidance on the surfacing of Bridleways and Horse Tracks.
Other comments | Ground conditions and drainage are critical when specifying trotting strips. Ground and existing drainage conditions are unknown at this stage. As such, further development of this specification may be required at a subsequent design stage.

## Resurfacing
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Resurfacing - Existing paved area
Construction only rate | 65
Unit | Per square metre
Specification | Plane off back to sub-base and replace a lower layer of bituminous material: 60mm thickness of AC20 (asphalt concrete with a 20mm stone size) overlaid by a thinner surface course: 20mm thickness of AC10 (10mm stone size).
Assumptions | - Some areas that are resurfaced are used as access routes. As such, the resurfacing specification is considered to be suitable for carriageway construction. - Sub-base is still suitable as a foundation
Exclusions | - Kerbing and edgings - Drainage - Fencing - Landscaping - Structures
Source Information | The rate is a median taken from 5 tender responses to a Sustrans project from 2019/20. The lowest tendered rate was £40, with the most expensive rate being £401.
Other comments | Specification may need to be changed depending on the level of vehicular access / traffic required. This is unknown at this stage and should be revisited at a subsequent design stage.

## Fencing
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Fencing (Timber)
Construction only rate | 36
Unit | Per linear metre
Specification | Timber post and rail fence with additional stock control wire netting. This specification of fencing is based upon Sustrans standard detail SD/32/B.
Assumptions | - Stock control netting is required. - Unit rate is for one line of fencing only. I.e. The rate for fencing on both sides of a path would need to be doubled. - Timber top rail included as most fencing will be erected alongside a shared use path. - Timber has already been treated with preservative.
Exclusions | Painting or other types of finishes.
Source Information | The rate is a median taken from 7 tender responses to two Sustrans projects from 2019/20. The lowest tendered rate was £16, with the most expensive rate being £53. This has been verified against 'Paths for All: Estimating price guide for path projects (2019)' which gives a total of £33 for a similar specification fence when using the upper costing limits.
Other comments | Omitting stock control netting would decrease the cost unit rate by approximately 15%.

## Modal Filter
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Modal Filter
Construction only rate | 18750
Unit | Number
Specification | Modal filter using standard pallet of Highway Authority materials i.e. granite/concrete kerbs and asphalt surfacing. Some basic greenspace improvements incorporated such as low level planting beds.
Assumptions | The suitability of a modal filter has stakeholder / community backing and has been successfully trialled.
Exclusions | - Traffic Regulation Orders - Legal Costs - Consultation / Engagement - Diversion or protection of utility apparatus
Source Information | The rate is a median average taken from a range of costs within: - Waltham Forest Mini-Holland Design Guide - Oxfordshire Liveable Streets: Florence Park Low Traffic Neighbourhood indicative scheme costing
Other comments | The modal filter could be replaced with a 'Basic' modal filter using bollards, signage and/or planters and trees. However, this approach would be recommended or suitable for a temporary trial should this be the preferred approach.

## Street Lighting
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Street lighting - within Highway
Construction only rate | 64
Unit | Per linear metre
Specification | Standard 6m high street light installed within the highway boundary.
Assumptions | - Typical residential street - Column spacing's at 30m - Not to used on main or major roads - Includes ducting and connections
Exclusions | - Temporary traffic management - Diversion or protection of utility apparatus
Source Information | The rate has been taken from information published by a English highway authority. This has been averaged against tendered rates for a school street project in Wales.
Other comments | Street lighting spacing is based on various factors including road geometry, column heights, lighting class and specification.

## Street Lighting Bollards
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Street lighting - low level bollard (rural environments)
Construction only rate | 50
Unit | Per linear metre
Specification | 80cm high, vandal proof, solar powered, motion detector bollard.
Assumptions | - Only to be used in rural environments to minimise ecological impacts. - No trenching, ducting or electrical connections required - 250-500 lumens output - 4m motion detector range, spacing's therefore set at 4m.
Exclusions | - Solar powered, does not require an electrical connection - Diversion or protection of utility apparatus
Source Information | Various
Other comments | There is very limited published information in relation to the costs of supplying and installing low level solar powered bollards. This is likely due to their limited use by local authorities across England, with most products of this type appearing within private developments, e.g. retail centre car parks. Research has found that costs vary from between £50 and £800 per unit (excluding installation), but the specification of these systems varies greatly. For the purposes of this cost estimate, a rate for a vandal proof system that has minimal maintenance requirements was considered most appropriate.

## Bus Gate
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Bus Gate
Construction only rate | 105000
Unit | Number
Specification | Bus gate with road markings and signage in accordance with the Traffic Signs Regulations and General Directions 2016 and Traffic Signs Manual.
Assumptions | - The suitability of a bus gate has stakeholder / community backing and has been successfully trialled. - The suitability of a bus gate has been subject to a wider traffic impact assessment. - ANPR cameras used as a means of enforcement.
Exclusions | - Traffic Regulation Orders - Legal Costs - Consultation / Engagement - Diversion or protection of utility apparatus - Operating / enforcement costs - Ongoing maintenance of hardware.
Source Information | There is very limited published information relating to the costs of installing a bus gate. Highway Decision Reports from various Highway Authorities across England, dating back to 2014, would suggest that the cost of installing a bus gate can vary between £70,000 and £140,000 per site. As such, this has been averaged to develop a rate that is considered suitable for this stage of design.
Other comments | Initial research would suggest that the maintenance of a bus gate over 5 years could cost a minimum of £20,000.

## Shared Path
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Shared Path (Conversion of existing footway)
Construction only rate | 242
Unit | Per linear metre
Specification | 2.2m wide footway construction into the carriageway with new full height kerb.
Assumptions | - Existing footway is approximately 1.8m wide (Taken from national average) - There is suffcient room within the carriageway to reallocate space to active travel - Inlcudes amendments relating to highway drainage - Includes provision of shared use signage.
Exclusions | - Temporary Traffic Management - Diversion or protection of utility apparatus
Source Information | The rate was applied to LCWIP works undertaken for a number of Highway Authorities across England during 2020/21.
Other comments | The width of footway and widening will vary from location to location. This rate has been developed on the assumption that most footways are around 1.8m wide. Therefore, this rate is considered a worst case scenario.

## Improve Existing Traffic Free
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Improve Existing Traffic-free Route
Construction only rate | 175
Unit | Per linear metre
Specification | 1m width of widening and 3m width of resurfacing.
Assumptions | - Flat ground - No major earthworks required - No retaining structures - Sub base will extend beyond the width of the path to provide sufficient edge support in lieu of a kerbed edge or channel. - Traffic loading not required.
Exclusions | - Kerbing and edgings - Drainage - Fencing - Landscaping - Structures - Diversion or protection of utility apparatus
Source Information | The rate has been developed using a pro-ratered 3m wide shared path rate, and the rate applied to general resurfacing.
Other comments | This rate has been developed on the assumption that the majority of traffic-free route requiring improvement through the route is around 2m width. In many cases, opportunities for widening these paths can be limited due to where they are situated. E.g. 2m wide paths situated in former rail corridors can mostly be widened to 3m prior to having negative ecological impacts. The rate has been developed on the basis that 1m of widening can be tolerated..

## Earthworks Ramp
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Accessible Ramp - Earthworks
Construction only rate | 1525
Unit | Per linear metre
Specification | Re-grade existing embankment to create a ‘zig- zag’ type ramp arrangement that will provide a connection over significant level differences, typically where the route moves between the highway environment and former rail corridor. In order to achieve suitable gradients; the ramps will typically follow a 1:20 gradient. The path on the ramp will be 3m wide and sealed.
Assumptions | - Some cut and fill works will be required to re-grade the embankment - Includes some provision for reinstatement of the existing landscape - Includes some provision for basic drainage and fencing.
Exclusions | - Design - Permissions and consents - Ecological mitigations. - Diversion or protection of utility apparatus
Source Information | The rate is a median taken from five tender responses to a Sustrans projects constructed in 2020/2021 . The lowest tendered rate was £246,537, with the most expensive rate being £407,914.
Other comments | Each site will different greatly in the level of earthworks requires to achieve suitable gradients. The rate developed is considered to be medium risk example of where some imported fill was required to make up levels. However, each site would require a more detailed assessment at a subsequent design stage, as it may be that more sever gradients are better addressed through the use of a structure.

## 3m Wide Shared Path on slope
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 3m wide Traffic-free Route (shared path).
Construction only rate | 510
Unit | Per linear metre
Specification | 150mm sub base with a single layer of 60mm thickness of AC14 (asphalt concrete with a 14mm stone size). Slopes built up and re-graded using imported fill. Fill material sloped back into existing ground profile using 1:2. Path to have 2.5% crossfall.
Assumptions | - Suitable for slopes up to 1:3. - Existing ground cannot be re-profiled - No retaining structures - Traffic loading not required. - New slope will be landscaped to suit surroundings.
Exclusions | - Kerbing and edgings - Fencing - Drainage - Structures - Diversion or protection of utility apparatus
Source Information | Rate derived using three tender responses to a path project in Scotland. These have been averaged against an earthworks rate taken from 'Paths for All: Estimating price guide for path projects (2019)'
Other comments | There may be opportunities to regrade existing slopes without effecting stability. This could result in a reduction of imported fill being required, which will reduce costs.

## Wayfinding Signage
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Wayfinding Signage
Construction only rate | 225
Unit | Number
Specification | 3mm thick aluminium plate, 75mm round galvanised steel pole with welded top cap, C16/20 concrete footing with 200mm surround.
Assumptions | - Minimum 2300mm height clearance for cycles (ground level to underside of plate) - Colours as per sustrans NCN standard - Includes reinstatement of existing ground
Exclusions | - Diversion or protection of utility apparatus
Source Information | The rate is taken from 'Paths for All: Estimating price guide for path projects (2019)'. The rate provided for a wayfinding sign is £200 and £250, with an average of £225.
Other comments | Wayfinding signage is assumed to be of a consistent size. As such, the post and foundations specified should be applicable across all sign installations.

## Security (Tunnels)
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Tunnel Security
Construction only rate | 20000
Unit | Number
Specification | CCTV camera site.
Assumptions | - One camera installed at each tunnel portal to monitor traffic entering / leaving the tunnels. - Camera installed every 500m. - Includes electrical and communications connection.
Exclusions | - Operation and maintenance costs.
Source Information | A conservative rate used by an English Local Authority has been applied in lieu of any further information being available.
Other comments | There is very little public information available to understand the costs associated with providing security measures within a former rail tunnel. The scope of this study has not enabled contact to be made with specialised security organisations to gain a better understanding of costs. Much of the costs will depend on the design of the system, which are unknown at this stage.

## Tunnel Works
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Tunnel Works
Construction only rate | 1766
Unit | Per linear metre
Specification | The rate has been developed to cover a combination of the following types of work: + Repointing + Brickwork repair + Brickwork replacement + Stonework replacement + SCL patch repairs + SCL full lining circumferential lining (deformed lining lengths) + ARMCO Backfill + Grouting (between brick leaves and external voids)
Assumptions | - Tunnels are considered to be in a 'poor to fair' or better condition. - The above measures will only be used as and when required. I.e., the rate does not consider shotcrete being used through extent of tunnels. - Tunnel drainage is no longer suitable and the path will need to be drained by alternative methods.
Exclusions | - Walking / Cycling path. This is included in another rate applied to each tunnel. - Path drainage, the walking and cycling path rate will include basic drainage, such as a gravity fed dish channel.
Source Information | The rate has been developed using: - Whitby to Staithes feasibility Study (Sustrans 2020) - Queensbury Tunnel Cost Comparisons (Queensbury Tunnel Society 2017) - Queensbury Tunnel Study (HRE-Jacobs 2021). - Queensbury Tunnel Phase 2: Technical Summary Structure Number: HQU/3D (AECOM 2018)
Other comments | The rates considered were as follows: + Queensbury Tunnel - BRB/Jacobs (2009). Minimalist scope to enable entry for inspections. £525 per lin/m. NOT INCLUDED. SCOPE DOES NOT CONSIDER REOPENING THE TUNNEL AS AN ACTIVE TRAVEL CORRIDOR. + Whitby to Staithes (Sandsend Tunnel). £861 per lin/m - NOT INCLUDED. W2S (Kettleness Tunnel) CONSIDERED A MORE CONSERVATIVE RATE + Queensbury Tunnel - QTS Engineering Team (2016). £1,229 - NOT INCLUDED. W2S (Kettleness Tunnel) CONSIDERED A MORE CONSERVATIVE RATE + Whitby to Staithes (Kettleness Tunnel). £1,502 per lin/m - INLCUDED AS THE LOWER LIMIT OF THE AVERAGED RATE + Queensbury Tunnel - AECOM (2018). £2,031 per lin/m - INLCUDED AS THE UPPER LIMIT OF THE AVERAGED RATE + Queensbury Tunnel - HRE/Jacobs (2021). £9,367 per lin/m - NOT INCLUDED. VARIENCE COMPARED TO OTHER SIMILAR STUDIES IS CONSIDERED TOO HIGH FOR THE PURPOSES OF THIS EXERCISE. + Queensbury Tunnel - HRE/Jacobs (2016). £15,470 per lin/m - NOT INCLUDED. CONSIDERED TO BE SUPERSEDED BY 2021 REPORT The rates estimated for the Whitby to Staithes tunnels are of the same magnitude to those developed by QTS in their 2016 report and those by AECOM in their 2018 report. The assessment undertaken by QTS considers the majority of the Queensbury Tunnel to be in a 'Fair' condition, whereas the condition of the Whitby to Staithes tunnels was considered to be 'fair to poor'. As such, when considering W2S and QTS rates, the rate of £1,502 per linear metre was considered to be a conservative but appropriate 'lower band' for the purposes of developing an averaged rate to apply to tunnels other than Queensbury Tunnel. The unit rate of £2,031 per linear metre has been applied as the upper band for the purposes of developing an averaged rate. The £9,367 rate developed as a part of the Jacobs 2021 reporting was considered to deviate too much from the studies undertaken by QTS, Sustrans and AECOM. As such, it was not considered as a part of this costing exercise. In practice, some structures will require more or less work than others. Therefore, whilst the rate may seem excessive for some of the better condition structures, this would be balanced out by a higher level of work being required in the more poor condition structures.

## 4m Wide Shared Tunnel Path
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | 4m wide Path in Tunnels (shared path).
Construction only rate | 240
Unit | Per linear metre
Specification | 225mm sub base with Two-layers of bituminous surfacing comprising a lower layer of a coarser bituminous material: 60mm thickness of AC20 (asphalt concrete with a 20mm stone size) overlaid by a thinner surface course: 20mm thickness of AC10 (10mm stone size). 2.5% crossfall towards gravity fed concrete dish channel (225mm wide).
Assumptions | - Follows longfall of former rail tunnels - No major earthworks required - No retaining structures - Considers traffic loading for maintenance and emergency vehicle access.
Exclusions | - Fencing - Landscaping - Diversion or protection of utility apparatus - Structural improvement works to tunnels
Source Information | The rate has been developed using information that was previously applied to a Sustrans study undertaken in Northumberland. The rate has been uplifted to account for the addition of drainage, which has been calculated using a median of five rates submitted as part of a tender exercise for a DfT funded Sustrans project.
Other comments | Where vehicle loading is not required, the path specification could be amended to a cheaper specification. However, at this stage it has been assumed that the paths within the tunnels will need to accommodate vehicle loading.

## Maintenance
Cost Estimate Rate Development | Queensbury Tunnel Feasibility Study
Title | Tunnel Maintenance
Construction only rate | 9.35
Unit | Per linear metre per year
Developed using | + Queensbury Tunnel - HRE/Jacobs (2021)
Rate build up | + Structural Examinations (aggregate of visual and detailed examination on a three year cycle) - £7,890/year + Drainage Maintenance £2,500/year + Periodic Repairs (aggregate of ten year cycle) £11,000/year
Assumptions | + Assumes that no pumps or ventilation is present within the tunnels. + Doesn't include maintenance of path side drainage, this is addressed within another rate.
%age rate to apply to non QT tunnels | 230m x £9.35 = £2,150.50 £2,150.50 / £406,180 (Construction cost) = 0.5%
Title | Non-Tunnel Maintenance (Traffic-free routes outside of the highway boundary)
Construction only rate | 2.35 per m²
Unit | Per square metre per year
Developed using | Paths for All: Estimating price guide for path projects (2019)'
Rate build up | Herbicide Application - 0.25 per m2 Litter pick - 0.15 per m2 Verge mowing - 0.35 per m2 Leaf Clearance - 0.10 per m2 Cut back of trees / shrubs - 0.07 per m2 Bound Surface Repair - 28.70 per m2
Assumptions | Assumes that bound surface repairs will only be required across 5% of the infrastructure per year. All other maintenance items are assumed to be required across 100% of the infrastructure.
%age rate to apply to non QT tunnels | 3m wide path - £2.35 x 3 = £7.05 / £155 = 4.55% 4m wide path - £2.35 x 4 = £9.40 / £188 = 5% 5m wide path - £2.35 x 5 = £11.75 / £230 = 5.11%