## Sheet1
Design Descision Log
Project: |  | 13358_Queensbury Tunnel Greenway Feasibility Study
Compiled by: |  | ML/AG/KA
Document ref: |  | 13358-DL-01
Date Updated: |  | 2021-10-10
No. | Decision Type | Segment Ref. |  | Design Decision | Standard | Justification | Alternative Solution | Discarded alternatives
|  | From | To
1 | Cycle Numbers | - | - | Assumed that <200 cycles an hour will be using the track. Therefore OK to base design widths and requirements off lower levels of cycle numbers. | - | Based on expectations of client
2 | Carriageway Cross Section | - | - | Where providing separated cycle tracks, general traffic lanes may be reduced to 3m unless stated otherwise, with remaining carriageway space given to cycle tracks.. | LTN 1/20 Table 7-2 | Traffic lane (bus route or >8% HGVs, or speed limit 40mph) Desirable minimum width - 3.2m Absolute minimum width - 3.0m
3 | Carriageway Cross Section | - | - | Footpath widths to be retained as existing for majority of the route. Where footpaths are to be impacted, widths will be provided as follows: Desirable min - 2m Absolute min - 1.5m | Inclusive Mobility Section 3.1 | As kerblines are to be retained where possible, footpaths will not be affected by design. Existing pedestrian / cycle shared space will be left as improved pedestrian facilities.
4 | Traffic Figures | - | - | Traffic data assumed for majority of on-road sections | - | There is little or no traffic data for the majority of roads and streets along the route. For these locations, traffic data has been assumed based on the place / function of the street and similar streets in the vicinity.
5 | Path width of traffic-free sections | - | - | Each section considered individually. Width availability and predicted use (taking into consideration links and urban/rural location) are main deciding factors in selecting widths. Considering these factors, provision falls into the following: - 4.5m width for shared use (cycles & pedestrians) with adjacent trotting strip. - 4.5m width for shared use (cycles, pedestrians, equestrians) where space is inadequate for separate trotting strip and equestrian use is expected to be light. - 3m width for shared use (cycles & pedestrians) with adjacent trotting strip where equestrian use is likely. - 3m width for shared use (cycles, pedestrians, equestrians). | LTN 1/20 | While the ideal is to provide separated infrastructure for cycles, equestrians and pedestrians along all sections of traffic-free path, cost and land availability often make this impractical. Additionally, where use is expected to be lower (at least initially), a lower grade of infrastructure is considered sufficient. Paths could potentially be widened at a later stage. | The provision of separated infrastructure (for cycles, equestrians and pedestrians) regardless of predicted use - this would have cost implications.
6 | Provision of trotting strips alongside traffic-free sections | - | - | Trotting strips have been proposed where available width is sufficient and where equestrian usage is expected to be higher (existing bridleways, rural areas and stretches linked by existing bridleways). Where available width is too limited and/or equestrian use expected to be lower, shared-use paths inclusive of equestrians are proposed. |  | While the ideal is to provide separated infrastructure for cycles, equestrians and pedestrians along all sections of traffic-free path, cost and land availability often make this impractical. Additionally, where use is expected to be lower (at least initially), a lower grade of infrastructure is considered sufficient. Paths could potentially be widened at a later stage. | The provision of separated infrastructure (for cycles, equestrians and pedestrians) regardless of predicted use - this would have cost implications.
7 | Surfacing of traffic-free paths | - | - | New path surfacing specified as asphalt in all locations. |  | A sealed smooth surface is more comfortable for scooters, adapted cycles, wheelchairs etc. | Crushed stone/stone dust surfacing or flexible resin bound surface. Choices have implications for capital and maintenance costs.
8 | Path width through tunnels | - | - | 4.5m shared-use |  | Assumption that equestrians will use tunnels. Assumption that some width will be required for drainage. Path width intended to be consistent through and between tunnels if possible. Tunnel widths not confirmed at this stage. | Reduce path width to minimum of 3m if space availability dictates. Provide separate equestrian strip if width availability allows.
9 | Lighting of traffic-free sections | - | - | Tunnels to be lit. Traffic-free sections predicted to be of commuter use have lighting proposed. Traffic-free sections predicted mainly to be of leisure use do not have lighting proposed. |  | The use of lighting increases security for users at night. It has been assumed that leisure use at night will be minimal. In areas where commuter use is likely, hours of work extend to darkness in winter.
10 |  | B101 | B104 | 4.5m wide shared-use path sections. Two-way cycle track between B102-B103. |  | Wider path supports likely higher use as in urban location. Two-way cycle track proposed through site of planning application development to provide separation from large goods traffic - Negotiation with developer required. | Use of Princeville Road to South if development precludes use of site. Would require additional provision on Ingleby Road (Princeville Road to B103).
11 | Path width | B108 | B111 | B108-B109: resurfacing of existing driveway. B109-B111: 3m wide shared-use path. |  | PRoW footpath status. B108-B109 requires vehicular access to properties to be maintained. Width restricted between B109 & B110, no separate trotting strip proposed. B110-B111 is proposed 3m wide for consistency.
12 | Path width | B111 | B113 | B111-B112: 3m wide shared-use. B112-B113: 4.5m wide shared-use. |  | Width availability and anticipated construction difficulties (due to gradient and retaining walls either sides) limit proposed width between B111 & B112 to 3m. Trotting strip excluded for this reason. | Consider reducing proposed width of B112-B113a to 3m for consistency.
13 | Route Option | B111 | H217 | Clayton Lane alignment selected in preference to Valley Bottom Option |  | Provides greater connectivity to population. Public support for use of Deep Lane previously demonstrated. Reduced flood risk. Reduced land availability risk. |  | Use of valley bottom with link along Hole Bottom Beck. Impact on landscape. Requires use of Brow Lane with poor visibility and challenging approach to GNRT.
14 | Path width | B113 | B113a, B114a, B115 | Main route proposed is B113-B115: 3m wide shared-use between B114 & B115; Separate trotting strip B114-B114a; 4.5m wide shared-use for remaining sections. B113-B113a is proposed as a link for connecting eastwards along Bradford Road. |  | Separate and stand-alone trotting strip proposed to enable a more direct link with west-bound bridleway at B114a, and to avoid horse use through residential section. B113 B113a discounted as main route for cycles and pedestrians due to insufficient width on Bradford Road between B113a and B117. | Consider reducing width of B113-B114 to 3m wide for consistency with east end and reduced intrusion.
15 | Route Option / Level of provision | B117 | B118 | Stepped 1-way cycle tracks on The Avenue | LTN 1/20 Table 4-1 | Assumed speed limit - 30mph Assumed traffic flow > 2000 Typical carriageway width is between 9 and 10m meaning there is sufficient space for two 3m general traffic lanes and a absolute minimum 1.5m wide one-way cycle track in each direction. | Utilise Clayton Lane. May require traffic calming measures in order to allow cycling in mixed traffic but does connect into more shops and destinations. Would also require roundabout crossing, rather than bypass, with associated cost implications. | Use of Reva Skye Lane. Width constraints at Clayton Primary School if crossing direct from B113a. Need to cross rather than bypass roundabout if linking from B116.
16 | Level of provision | B118 | B119 | Shared use footway on the western side of Baldwin Lane. | - | Provides continuous connection between traffic-free section and proposed separated infrastructure on The Avenue. There are no side roads on this section so a continuous route can be provided. | Improved provision built into future local plan development. | Traffic free path in land to west of Baldwin Lane. Properties at north and south prevent provision along whole length.
17 | Route Option | B118 | B123 | Use of Baldwin Lane and RoW to Station Road | - | Considered most likely option for accessible provision in available landscape. |  | Brook/Brow Lane and fields to south. Narrow highway with no space for separation. Gradients in fields between lane and Station Road are steeper than selected route.
18 |  | B119 | B123 | Resurface B119-B120. B120-B123: Realign and upgrade existing PRoW footpath to a 3m wide shared cycle/walking path with adjacent trotting track. |  | PRoW footpath status. Realignment in places required to obtain desired 1:20 gradient and to minimise infringement through properties where possible. Trotting track to be provided if width permits. | Exclude trotting strip if width is found to be too limited.
19 | Route Option | H101 | H102 | Shared use footway on the eastern side of the carriageway | - | Provides continuous connection from NCN on Gaukroger Lane and proposed traffic-free route adjacent to Discover Road and bypasses the existing roundabout at Water Lane
20 | Level of provision | H108 | H112 | Cycling in Mixed Traffic Environment. Modal filter provided at H111, reduced speed limit. | - | Speed limit - 30mph Assumed traffic flow < 2000 Carriageway width prevents separated infrastructure being provided. Modal filter and reduced speed limit would ensure route suitable for most users.
21 | Route Option | H108 | H112 | Route utilises the whole length of Old Lane between Halifax town centre and the proposed greenway connection to Queensbury Tunnel. | - | Old Lane is an existing road running parallel to Ovenden Brook and A629. The road is already relatively quiet but can be made quieter through traffic calming interventions already proposed as part of North Halifax Improved Streets for People scheme. Road is already existing as opposed to proposed Ovenden Brook traffic-free route. No land ownership issuers. Heritage value as provides good views across valley and at disused mills. Opportunity to phase works by connecting into TCF scheme at Broad Tree Road / Ovenden Way before future funding for off-road connection to School Cote Brow becomes available. Reconfiguration of Ovenden Way / Ovenden Road / Broad Tree Road junction to improve connection for cycles. |  | Traffic-free route adjacent to Ovenden Brook. Land ownership issues. Potential safety issues due to close proximity to disused factory. In / Near to flood zone. Multiple crossings of beck required. Site passes through wooded areas. Earthworks / Structural Ramp required to join into Old Lane / traffic-free route.
22 | Level of provision | H112 | H116 | Route access ramp may be required at south end. 3m wide shared-use path across hillside. H114-H115 is on-road, quiet residential street. Short cobbled section at crossing of Churn Milk Lane. |  | 3m width proposed due to cost, visual impact and extent of works associated with construction across hillside, steep in places. Trotting strip excluded for this reason. | Wider infrastructure with more substantial retaining walls / earthworks at significantly higher cost.
23 | Route Option | H115a | H116 | Alignment along hillside, avoiding Holdsworth Lane, Brow Lane, School Cote Brow |  | Hillside alignment reduces approach gradients and provides crossing point with visibility for approaching traffic. Gradient of Brow Lane steep. Insufficient width for separated provision (reported high levels of cut-through traffic on Brow Lane). Poor visibility exiting School Cote Brow travelling South.
24 | Level of provision | H116 | H215 | 3m wide shared-use path. H214-H215 requires route access ramp through old quarry site. |  | Alignment to attain 1:20 gradient. Consultation with landowner regarding planning application required.
25 | Level of provision | H116 | H117 | 3m wide shared-use path. Indicative alignment shown; 1:20 gradient desired. North end utilises existing PRoW bridleway and path (with upgrade) where possible. Lighting along whole section. |  | Construction on steep hillside location will require extensive works. Wider provision and trotting strip discounted for this reason. | Wider infrastructure with more substantial retaining walls / earthworks at significantly higher cost.
26 | Route Option | H118 | H128 | Route utilises short off-road sections ( across Shibden Brook and adjacent to Trinity Academy Bradford) and quiet streets (Shibden Head Road, Long Lane, new housing estate) to travel through Queensbury as opposed to Halifax Road / West End route | LTN 1/20 Table 4-1 | The proposed alignment takes users away from busy sections of road. The section on Long Lane also provides a focal point for the route with stunning views across Shibden Valley. Modal filters are proposed on Long Lane to remove through traffic and create a quiet / safe environment for users. The proposed route option ties in to 'The Bike Mill' repair shop which could act as a hub on the route. While the proposed section in isolation does not meet the requirements of LTN 1/20 in terms of directness, if viewed in the context of the entire route, the proposed deviation is negligible but provides benefits to users in terms of safety and comfort. Spurs from the proposed route can be provided into the residential areas of Queensbury. |  | Most direct route would be via Halifax Road / West End. This alignment would require separated infrastructure based on LTN 1/20 Table 4-1. Pinch points identified before and after Hill End Lane where separated infrastructure could not be provided. Providing separated infrastructure would require removal of on-street parking for the majority of this section, with little/no alternative for residents on the section.
27 | Route Option | H203 | H204 | Use of TCF proposals. |  | High likelihood of provision being developed. | Creation of ramp from Shroggs Road to Old Lee Bank for quieter alternative at greater cost. Relatively unlikely to be provided in light of TCF scheme.
28 | Route Option | H212 | H115a | On-road route connects in to the greenway route between Halifax town centre and Queensbury tunnel entrance | - | Route ties in to traffic-free route to provide a more comfortable connection for users as opposed to the relatively congested and very steep sections of Windy Bank Lane to School Cote Brow | Utilise Holdsworth Road and Brow Lane to access School Cote Brow and the Queensbury Tunnel Entrance / 'Alpine Climb'. Provides opportunity for works to be phased as route to Halifax can connect into on-road route via Beechwood Park until the proposed greenway option to Old Lane is constructed, but is not preferred option due to lmitations described in No. 23.
29 | Crossing | H212 | 212 | Crossing relocated and upgraded to a Toucan crossing | LTN 1/20 Table 10-2 | Crossing moved closer to the desire line for users. Upgraded to a signalised crossing based on assumed traffic figures.
30 | Route Option | H212 | H207 | Proposed route passes through Beechwood Park and quiet streets to connect into proposed TCF route on Cousin Lane | LTN 1/20 Table 10-2 | Route ties in to Beechwood Park BMX track. Provides on-road route requiring minimal intervention (Roads have 20mph speed limit and assumed that traffic figures < 2000). Existing modal filter on Moor Lane. Signalised crossing provided at Keighley Road based on assumed traffic figures. |  | Traffic-free route via Illingworth Sports and Social Club. Unnecessary land taken when suitable on-road option possible.
31 |  | H215 | H217 | 4.5m shared-use track through tunnel and at north end. Lighting through tunnel. |  | Assumption that Queensbury Tunnel can be utilised. 4.5m wide if possible, given length. | 3m wide shared-use if width is limited. Separate trotting strip if width allows.
32 | Route Option | K101 | K104 | Cycling in mixed traffic. Bus gate provided on Parkwood Street and modal filter proposed on Low Mill Lane | LTN 1/20 Table 4-1 | Provision of filters would remove through traffic from proposed route, most importantly it would remove industrial traffic. A new filter would be supported by the location of Parkwood Primary School. Would also create good separation between residential and industrial sections of Parkwood Street. Alternative motor vehicle access available via A6035 and Airevalley Road. |  | Cross Street/Grace Street ascent between Pitt Street and Parkwood Road. It was determined that gradient benefits did not outweigh risks of further ingress into industrial estate.
33 | Route Option | K104 | K105 | Shared space area on the eastern side of the carriageway. | - | Insufficient space on Park Lane to provide separated cycle infrastructure as would be required by LTN 1/20 Table 4-1 based on assumed traffic speeds and traffic low. No alternative route to direct traffic. Tightening kerb lines at junction with Hainworth Wood Road North would create adequate space for crossing of Park Lane. Shared space area on east of Park Lane would provide direct connection to Parkwood Street and on to Keighley Train Station
34 | Route Option | K105 | K106 | Existing environment on Hainworth Wood Road North is suitable for cycling in Mixed Traffic. Therefore minimal intervention would be required. | LTN 1/20 Table 4-1 | Speed limit - 20mph Assumed traffic flow < 2000
35 |  | K106 | K109 | Resurface north and south ends where some surfacing already exists. 3m wide cycle/pedestrian shared-use path plus adjacent trotting strip proposed. |  | Currently highway despite being mostly unsurfaced and unsuitable for motor vehicles. Town edge / rural location and predicted horse use. | Increase cycle/pedestrian path to 4.5m width if space permits. | Use of full length of Hainworth Wood Road and Hainworth Lane. Steep cobbled ascent without benefits of being traffic-free.
36 | Road Closure | K107a | K107a | Provision of a modal filter on unadopted road | - | Little / no traffic currently uses the unadopted road due to its poor current state. Resurfacing works as part of the route development may lead to cars using the road again. Provision of a modal filter will prevent this.
37 | Route Option | K109 | K110 | Use of highway for mixed traffic environment. |  | Existing environment likely to be suitable to mixed traffic environment. Potential to reduce vehicle speeds if required. | Traffic-free link across fields may be possible with extensive earthworks, with implications for cost.
38 | Level of provision | K110 | K112 | Resurface north end. 3m wide shared-use path with fencing where required. |  | North end requires vehicular access retaining for residents. Has PRoW footpath status. Width availability and banks both sides restrain width increase, therefore no trotting strip included.
39 | Route Option | K112 | K114 | Cycles stay on the road between Sugden House Farm and off-road section to Moor Bottom Lane via Bingley Road | - | 20mph speed limit extended past the diversion to the traffic-free route to Moor Bottom Lane. Existing traffic calming measures on Bingley Road can be revisited to create a safe environment for cycle. Short section of potentially substandard cycle route is acceptable in order to connect a much wider network. Works can be phased and a more suitable traffic-free route across the fields between Sugden House Farm and Moor Bottom Lane can be investigated when future funding is announced. | Traffic-free route between Sugden House Farm and Moor Bottom Lane. Increases the amount of climbing required by cycles. May require significant cutting on approach to Bingley Road. Land ownership challenges.
40 | Level of provision | K114 | K115 | Resurface existing track. |  | Vehicular access to be maintained for farms/properties at east end. Vehicular use is expected to be minimal - no through way for traffic. PRoW Bridleway status. | Gradient is steep. provision of resting platforms, a footpath and/or trotting strip alongside road and/or in adjacent fields could be considered but at higher cost and may also result in higher vehicular speeds.
41 | Level of provision | K115 | K116 | 3m wide shared-use path. |  | Would fit inside existing fenced-off area; east end is restricted in places by stone walls. Current PRoW bridleway status. No width availability for additional trotting strip. | 4.5m wide shared-use path and/or additional trotting strip - would require agreement of additional land use by land owner.
42 | Level of provision | K116 | K119 | Resurface existing track. |  | Good width available, vehicular access required for nearby properties (K116-K117 is private driveway and hasn't been assessed). Vehicular use expected to be minimal. | K116-K117 is the preferred route as follows line of dismantled railway but if discounted at a later stage, investigate use of bridleways in vicinity. | Existing bridleway between K116 to K117. Similar landowner requirements along with additional infrastructure requirements.
43 | Level of provision | K118 | K118 | Uncontrolled crossing |  | Farm access track. Levels of traffic expected to be very low.
44 | Level of provision | K124 | K126 | 3m wide shared-use path. No separate trotting strip. |  | PRoW bridleway status. Hillside location would make wider path more costly and invasive.
45 | Level of provision | K126 | K127 | Resurface existing track. |  | PRoW footpath. Driveway to residential property, vehicular use to be maintained.
46 | Level of provision | K127 | K130 | Route access ramp at north end; 3m wide track with adjacent trotting stip. |  | PRoW footpath is located along part of west edge of rail embankment/cutting but is narrow. Widening would be difficult given hillside location. Part utilises quarry access road (also PRoW footpath). Flatter more suitable space is assumed on rail alignment. Ramp required to reach this at north end. Assumption that width will be available on old rail alignment (accessing for assessment of most of the alignment has not been possible due to private land ownership).
47 | Level of provision | K130 | K130a | Route access ramp proposed to create a link to Foster Park View. Assumed width availability will be too restricted for separate trotting strip. |  | Link would enable connection with Denholme and Doe Park Water. Route has not been accessible for assessment; assumption that land can be obtained and construction achievable. | An alternative link joining Foster Park View further east could be possible but would then entail more extensive use of the steep Foster Park View to reach Denholme.
48 | Level of provision | K130 | K143 | 4.5m wide shared-use path through and between tunnels / inverted arches. Lighting through tunnels / inverted arches. K137-K138 aligns through proposed housing development. |  | Assumption made that width continuity is available along old rail alignment. Assumption that old rail alignment and associated tunnels can be utilised. Further investigations required to confirm. Likely to be area of higher user numbers, hence greater width required. | Additional trotting strip if space is available. | Various alternatives avoiding Well Heads Tunnel. Gradients/constructability and highway constraints justify exploration of use of tunnels for more suitable provision.
49 | Level of provision | K147 | K148 | Station Road: existing on-road NCN. Resurface. |  | Steep gradient but no-through-way - therefore vehicular use expected to be minimal. | Good width available in verges - resting platforms and handrails in the verge could be created.